## README
Worldosphere launch workbook — generated from the planning package (tools/gen_workbook.py). Editable: add your own rows freely.
Sheets: Calendar · Fallback calendar · Briefs · Reserves · Topic pool · Claims · Schedule · Pilot hours · Tracking · QA log · Change log · Asset register.
Yellow cells are for you to fill in. Formula columns (rates per 1,000 engaged views) calculate automatically.
Definitions and denominators: 21_Measurement_and_Iteration_Plan.md §1. Nothing in this workbook is a prediction or a published metric.
Source of truth for regenerated sheets: tools/calendar_data.py, tools/ledger_data.py, data/*.csv. If you edit those, re-run the generator into a NEW file name so your filled-in sheets are not overwritten.
Generated: 2026-10-14 (planning date).

## Calendar
Day | Date | Weekday | Topic and angle | Recommended title | Content pillar | Chosen hook | Main payoff | Target duration | Reason for placement | Production complexity | Main test | Brief ID | Lead | Recipe | Verdict | Kits | Claims | Reserve replacement
1 | 2026-10-31 | Sat | Halloween outbreak: in a street full of zombie costumes, the only reliable tell is breath in the cold air | Zombie Outbreak on Halloween: How Do You Tell Who's in Costume? | P1 OUTBREAK | Diegetic contradiction: a city alert reading 'AVOID ANYONE ACTING STRANGELY' held up against a street full of costumed zombies | The breath test sorts costumes from the Turned; Kai gets Mia home; final image: a hand pressed to the cold window leaves no fog | 60–64 s | Halloween is the single most relevant day of the year for this premise and falls on a Saturday. It shows the whole channel promise at once: an ordinary place, a clever rule-based decision, the Fork, the Verdict and the cast. | H (pre-built before launch) | Diegetic-contradiction hook + planted 'rewatch' details (non-breathing figures in early shots) | WS-001-BRIEF | Kai + Mia | R-A Location Outbreak | SURVIVED — He watched their breath, not their costumes. | K1 suburban night street + house; K10 crowd/Turned; K9 HUD | C-101, C-102, C-103, C-104 | R04 Gas Station, 2 A.M. (if launch slips past Halloween, Day 1 becomes WS-003)
2 | 2026-11-01 | Sun | A car goes into water: the door won't open, and the window is the way out within about a minute | Your Car Is Sinking. You Have About One Minute. | P2 REAL RULE | Frame 0 is underwater: the car is nose-down, Owen's face is lit by the dash, and a timer reads ≈1:00 | Owen tries the door (pinned by water pressure), switches to the side window with his keyring punch and escapes before the waterline reaches the glass | 56–60 s | It is a universal fear with immediately useful, verified facts (C-201–206). It shows the channel isn't only zombies, while keeping the decision format. 1 Nov is the first evening after US clocks fall back, which explains the early darkness. | M | Countdown HUD opening in the middle of the event; Real Rule card | WS-002-BRIEF | Owen | R-D Countdown | ESCAPED — He went for the window, not the door. REAL RULE: Car in water: get out through a side window in the first minute. | K2 car interior/road/water; K9 HUD | C-201, C-202, C-203, C-204, C-205 (BLOCKING order check), C-206, C-207 | R02 Six Inches of Water
3 | 2026-11-02 | Mon | Everyone says the warehouse superstore is the best place to survive; that's exactly why it isn't | Everyone Says the Superstore Is the Best Place to Survive | P1 OUTBREAK | Cutaway of a giant store at dawn as hundreds of headlights converge on it: 'Everyone says the superstore is the best place to survive. Everyone else says it too.' | Tess drives away from the store with a family. From the ridge, the store's noise Sphere pulls in the whole town; her delivery van is full of supplies | 58–62 s | It's the most familiar zombie debate after 'where would you hide'. Using a different lead and setting from Days 1–2 shows the anthology cast. The daylight palette contrasts with Day 1's night. | H (pre-built before launch) | 'Everyone says…' debate premise: comment volume and shares | WS-003-BRIEF | Tess | R-A Location Outbreak | ESCAPED — The best spot was the one nobody picked. | K3 store + loading dock + lot; K10 crowd; K9 HUD/map | C-012, C-013 (Sphere scale), C-102/103 rules (WR-03, WR-07) | R03 Day 12: A Knock on the Hatch
4 | 2026-11-03 | Tue | Earthquake: why the doorway is a myth in modern buildings, and what to do instead | Why You Shouldn't Run to the Doorway in an Earthquake | P2 REAL RULE | Frame 0: café, cups rattling, Kai halfway to a doorway. Hook card 'THE DOORWAY MYTH' | Kai drops under a table and holds on as it shifts; the doorway door swings shut on the spot he was heading for; then an aftershock | 48–52 s | A well-known myth with fully verified facts (C-401–404). It is quick to produce and keeps week 1 alternating between fiction and real. | L | Myth-busting hook in P2 (compare with Day 8) | WS-004-BRIEF | Kai | R-B Real Rule | SAFE — He dropped, covered and held on. REAL RULE: Earthquake: Drop, Cover, Hold On — not the doorway. | K4 café interior (reusable as diner/café later); K9 | C-401, C-402, C-403, C-404 | R01 Lightning
5 | 2026-11-04 | Wed | Winter-storm blackout: a neighbour's generator in a half-open garage fills the house with carbon monoxide | The Blackout Mistake That's More Dangerous Than the Storm | P2 REAL RULE | Frame 0: a dark snowy street with one warm, glowing house; its garage door is half open with a generator running; a violet Sphere seeps into the rooms | Owen gets the family into fresh air first, calls for help and moves the generator at least 20 ft away | 56–60 s | It's seasonal (early winter storms) and verified (C-501–504). The house/suburb kit is reused from Day 1. It is the first Owen 'expert' moment. | M | Gas (violet) Sphere comprehension; warning-style hook | WS-005-BRIEF | Owen | R-B Real Rule | SAFE — He got them into fresh air first. REAL RULE: Never run a generator in a garage. Keep it 20+ ft from the house. | K1 street (snow variant); K4 interior; K9 | C-501, C-502, C-503, C-504, C-506 (BLOCKING: fresh air + call for help); C-505 (BLOCKING if alarms mentioned) | R08 Cold Water Overboard
6 | 2026-11-05 | Thu | An outbreak on a plane four hours from landing: no exits, one aisle, and beverage carts | A Zombie Outbreak at 35,000 Feet: What Would You Do? | P1 OUTBREAK | 'Four hours from landing, the man in 31B stopped breathing. Then he stood up.' (frame 0: aisle view, seatbelt sign on) | Tess builds a wall of braked carts across the aisle; the Turned can push but can't climb; the plane lands behind the barrier | 62–66 s | A high-concept premise everyone can picture, scheduled after the kit-build buffer. It keeps outbreak episodes spaced every 2–3 days in week 1. | H | 'What would you do?' question title; confined-space story | WS-006-BRIEF | Tess | R-A Location Outbreak | SURVIVED — She stopped running and built a wall. | K8 plane cabin (modular row); K10; K9 | C-102, C-103 (WR-04 push vs climb) | R09 Cruise Ship, Day 3
7 | 2026-11-06 | Fri | Outbreak in your street: hide on the roof or in the basement? We play both endings | Roof or Basement? We Played Both Endings | P1 OUTBREAK | Frame 0 is already split by the Fork: roof hatch on the left, basement stairs on the right, Kai and Mia in the middle | Roof: cold, loud and exposed, but reachable only by a ladder the Turned can't climb, and visible to rescuers (SURVIVED). Basement: warm and quiet, but one push-door they can force (TRAPPED) | 68–72 s | It closes week 1 with the format most likely to drive comment debate, and reuses the Day 1 house and street kit. | M | Both Endings format baseline (retention through the 'rewind') | WS-007-BRIEF | Kai + Mia | R-C Both Endings | ROOF: SURVIVED · BASEMENT: TRAPPED — Pick the place they can't climb to. | K1, K4 (house section), K10, K9 | C-103 (WR-04), WR-03 | R06 Your First Move (three endings)
8 | 2026-11-07 | Sat | Tornado on the highway: why the overpass is the worst shelter, and what to do in a vehicle | Why the Highway Overpass Is the Worst Place in a Tornado | P2 REAL RULE | Frame 0: a funnel on the horizon; cars pulling in under an overpass; Tess's van slowing; a phone WARNING card | Tess doesn't stop under the bridge; traffic blocks her escape, so she gets into a ditch lower than the road and covers her head | 54–58 s | It reuses the vehicle kit from Day 2 after a 6-day gap. November is a secondary US tornado season [BK]. The facts are verified (C-801–804). | M | Second myth-busting P2 (compare with Day 4); red wind Sphere | WS-008-BRIEF | Tess | R-B Real Rule | SURVIVED — Lower than the road, not under it. REAL RULE: Tornado: never shelter under a highway overpass. | K2 van/road; K6 open plains; K9 | C-801, C-802 (confirm wording), C-803, C-804 | R02 Six Inches of Water
9 | 2026-11-08 | Sun | The boat plan: the Turned can't swim, but they don't breathe either, so they walk the bottom, and the tide matters | Zombies Can't Swim. So Why Wasn't the Boat Safe? | P1 OUTBREAK | Frame 0: night harbour; Owen's sailboat anchored 100 m out; the Turned on the dock: 'They can't swim. That's why Owen anchored a hundred metres out.' | Owen notices the tide table and moves to deep water before low tide; at low tide his old anchor spot is ringed with heads just breaking the surface | 58–62 s | It rewards Day 1 viewers (no-breath rule) while standing alone, and changes setting to water and night after two daytime episodes. | M | World-rule payoff twist (WR-02 callback from Day 1) | WS-009-BRIEF | Owen | R-A Location Outbreak | ESCAPED — He checked the tide, not just the distance. | K7 harbour/boat; K10 (Turned underwater variant); K9 | C-102 (WR-02), WR-04 | R03 Bunker Hatch
10 | 2026-11-09 | Mon | A multi-day blackout, hour by hour: what fails first in your home and what order to act in | When the Power Goes Out for Days, This Is What Fails First | P3 WORLD SHIFT | Frame 0: a house cross-section the instant the lights die; a T1 clock reads HOUR 0: 'Your house doesn't fail all at once. It fails in order.' | By hour 72 they've lost almost nothing, because they acted in order: water, cold food (doors shut), no generator indoors | 62–66 s | It opens week 2 with the World Shift pillar after five fiction/real alternations. It reuses Day 5's verified blackout facts with a different angle (planning, not CO). | M | Hour-by-hour ladder format (P3 baseline) | WS-010-BRIEF | Kai + Mia (Owen cameo) | R-E World Shift ladder | SAFE — They planned by the hour, not the day. REAL RULE: Fridge about 4 h; full freezer about 48 h. Keep the doors shut. | K4 house cross-section; K9 clocks/counters | C-1001, C-1002, C-011, C-022, C-501/502; C-1003 must be cut or verified | R08 Cold Water Overboard
11 | 2026-11-10 | Tue | High-rise outbreak: everyone heads for the roof; Tess stays on her floor and lets the stairwell door do the work | Zombie Outbreak in Your Apartment Building: Go Up or Down? | P1 OUTBREAK | Frame 0: building cross-section, red dots in the lobby, arrows 'UP?' 'DOWN?', Tess at her door on 14: 'Everyone in the building had the same plan.' | The roof crowd's noise draws the Turned upward past floor 14; Tess's floor stays sealed because from the stairwell the door must be pulled | 58–62 s | This has the strongest retrieved demand signal for a location debate. It sits mid-week-2 after a P3 day and before a P2 day. | M | Up-vs-down debate premise ([R-S38] evidence) | WS-011-BRIEF | Tess | R-A Location Outbreak | SURVIVED — She let the stairwell door do the work. | K5 tower cross-section/stairwell/corridor; K10; K9 | C-103 (WR-04); C-1101 (in-story fact only) | R04 Gas Station
12 | 2026-11-11 | Wed | House fire at 3 a.m.: a closed bedroom door can keep a room hundreds of degrees cooler | House Fire at 3 A.M.: The One Thing That Buys You Time | P2 REAL RULE | Frame 0: split cutaway of two bedrooms, one door open and one closed, with smoke filling the hallway; a T1 timer reads 02:00 | Owen, who sleeps with his door closed, stays low, sees smoke in the hall and escapes through the window; outside, he doesn't go back in | 54–58 s | Heating season; verified facts (C-1201–1204). It is the strongest share-to-protect candidate in week 2. | M | Split-screen comparison opener | WS-012-BRIEF | Owen | R-B Real Rule | SAFE — His door was closed before the fire started. REAL RULE: Sleep with the door closed. Get out, stay out. | K4 house cross-section (night); K9 | C-1201, C-1202, C-1203, C-1204, C-1206 (BLOCKING: window as second way out); C-1205 only if verified | R01 Lightning
13 | 2026-11-12 | Thu | Outbreak during a horror film: the loudest room in town, and the exit door that only opens one way | Zombie Outbreak in a Movie Theater: Nobody Noticed the Screams | P1 OUTBREAK | Frame 0: dark auditorium, a screaming face on screen; in row C a Turned leans toward a viewer; Kai in the back row notices | Kai leads six people out the push-bar emergency exit; the Turned in the lobby can't pull it open from outside | 58–62 s | This has an evergreen entertainment premise. After two serious days it lightens the tone. It reuses push/pull logic in a new place. | M | Comedic-irony hook | WS-013-BRIEF | Kai | R-A Location Outbreak | ESCAPED — He picked the door that opens one way. | Theater interior (new, simple tiers); K10; K9 | WR-03, WR-04; C-1101 (in-story only) | R07 Wedding Reception
14 | 2026-11-13 | Fri | You get seven days of warning before an outbreak: lock down in the city or leave early? Both endings | 7 Days of Warning Before the Outbreak: Stay or Leave? | P3 WORLD SHIFT | Frame 0: a '7 DAYS' calendar flip and a leaked memo on Tess's phone, with the Fork already split: CITY vs COUNTRY | Stay: a stocked apartment, but the dense city falls first and the supplies run out (TRAPPED). Leave on Day 2, before the panic: clear roads to Owen's cabin (SURVIVED) | 68–72 s | 'Advance warning' has retrieved interest [R-S29] and the Cornell model gives real context (C-1401). It closes week 2 with a big-picture debate. | M | Both Endings on a P3 premise (second data point) | WS-014-BRIEF | Tess | R-C Both Endings | STAY: TRAPPED · LEAVE EARLY: SURVIVED — Leaving early beats leaving fast. | K5 apartment; K2 road; K6 cabin exterior; K9 map | C-1401 (qualified), C-1002, WR-08 | R06 Your First Move
15 | 2026-11-14 | Sat | Antarctic research station with zero cases until the last supply plane lands with a bandaged passenger | The Last Place on Earth Without the Outbreak (Part 1) | P1 OUTBREAK (SAGA) | Frame 0: plane landing on an ice runway at dusk; HUD 'OUTBREAK DAY 9 · STATION ZERO: 0 CASES' | Owen reads the fever and the bandage; the man turns in the medical bay, and Owen seals it in time (CONTAINED). New problem: the bay sits next to the heating plant | 66–70 s | This is the planned serialization test, placed mid-month once the baseline formats have data. It is weekend viewing (Sat/Sun pair). | H | SAGA Part 1: does a resolved Part 1 with a forward line lift Part 2 views and follows? | WS-015-BRIEF | Owen | R-F Two-part Saga | SURVIVED — Owen read the bandage, not the smile. (Forward line: 'The heat runs out in 30 hours.') | K6 snow/ice + station interior (new); K10; K9 | WR-01 (fever, bite), WR-04; C-1501 (no real numbers unless verified) | R05 The Crossing (original puzzle)
16 | 2026-11-15 | Sun | Station Zero, part 2: heat runs out in 30 hours and the only weapon is the cold | Station Zero Part 2: The Only Weapon Was the Cold | P1 OUTBREAK (SAGA) | Frame 0: Owen in a parka at the boiler-room hatch; T1 'HEAT: 30 HOURS'; story thermometer 'OUTSIDE −41°C' | Owen shuts the medical wing's heat and opens its outer door; the Turned frosts over and stops (WR-06); he passes it, restores the heat, and twelve people survive | 66–70 s | This is the second half of the saga test. A one-line in-world recap keeps it standalone. | M (reuses Part 1) | SAGA Part 2: retention of cold viewers; Part2/Part1 view ratio | WS-016-BRIEF | Owen | R-F Two-part Saga | SURVIVED — He turned the cold into a wall. | Station kit from Part 1; K9 | WR-06; WR-02 (frost/no breath); C-1501 | R03 Bunker Hatch
17 | 2026-11-16 | Mon | Rip current: the instinct to swim straight back is the one that exhausts swimmers | Caught in a Rip Current? Don't Swim Back to Shore. | P2 REAL RULE | Frame 0: overhead beach; Kai being pulled outward inside a narrow cyan Sphere channel: 'Every instinct said swim straight back.' | Kai floats, calms his breathing, swims parallel out of the narrow channel, then angles back to shore | 50–54 s | Verified facts (C-1701–1703). After the saga weekend it returns to a short, clear standalone. Evergreen (Southern Hemisphere summer approaching). | M | Water Sphere + swimmer POV; Real Rule after the saga weekend | WS-017-BRIEF | Kai | R-B Real Rule | SAFE — He swam sideways, not against it. REAL RULE: Rip current: don't fight it. Float, then swim parallel to shore. | K7 beach/ocean overhead; K9 | C-1701, C-1702, C-1703; C-1704 not animated unless verified | R08 Cold Water Overboard
18 | 2026-11-17 | Tue | A flash in the sky (meteor airburst): the shock wave arrives later, and windows are the danger (Chelyabinsk 2013) | If You See a Flash in the Sky, Don't Go to the Window | P2 REAL RULE | Frame 0: an office; a white flash across the windows; everyone turning toward the glass: 'When the sky flashes, everyone goes to the window.' | Tess moves away from the glass to an interior wall; the delayed shock wave blows the windows in; she's unhurt | 52–56 s | Leonid meteor-shower week brings meteor curiosity [BK]. The script must state that shower meteors are harmless dust (C-1802). Conditional on verifying C-1801. | M | Historical-reference hook ('In 2013…') in Leonid week | WS-018-BRIEF | Tess | R-B Real Rule | SAFE — Away from the glass, not toward it. REAL RULE (pending verification): A bright flash in the sky? Stay away from windows. | K5 office interior; K9 | C-1801 (BLOCKING), C-1802 (BLOCKING) | R01 Lightning (verified)
19 | 2026-11-18 | Wed | Stuck in an elevator between floors as the outbreak begins: the steel box nobody can open | Stuck in an Elevator When the Outbreak Starts | P1 OUTBREAK | Frame 0: elevator interior, flickering lights, Mia pressing the alarm, floor display '7½', muffled shuffling above: 'For once, that was good luck.' | They don't pry the doors; they stay quiet; the Turned can't open elevator doors; firefighters with keys open the doors hours later | 52–56 s | A cheap episode in a busy week (between two P2s and a P3). Verified elevator facts (C-1901/1902) are combined with WR-04. | L | Low-cost single-set episode: performance vs production cost | WS-019-BRIEF | Kai + Mia | R-A Location Outbreak | SURVIVED — They stayed in the box nobody could open. REAL RULE: Stuck in an elevator? Stay in, use the alarm, don't force the doors. | Elevator interior (new, tiny); K10 (sound only + feet in door gap); K9 | C-1901, C-1902, WR-03, WR-04 | R04 Gas Station
20 | 2026-11-19 | Thu | A solar superstorm: low-latitude auroras, stressed transformers and a long outage. What a lineman does first | What Would a Massive Solar Storm Do to the Power Grid? | P3 WORLD SHIFT | Frame 0: green aurora over a southern town, people filming; Owen listening to a humming transformer: 'Everyone was filming the sky. Owen was listening to the transformers.' | Owen treats the aurora as a warning: water, fridge rules and checks on the neighbours before the outage spreads | 60–64 s | A big-picture P3 in week 3. Conditional on verifying C-2001; swap to R01/R08 if verification fails. | M | Spectacle visual (aurora) hook in P3 | WS-020-BRIEF | Owen | R-E World Shift ladder | SAFE — The lights were a warning, not a show. | K1 town (night variant); K4; K9 map | C-2001 (BLOCKING), C-1001, C-1002 | R01 Lightning
21 | 2026-11-20 | Fri | Falling through early ice: control the gasp, then turn back toward the ice that held you | Fell Through the Ice? Turn Back the Way You Came. | P2 REAL RULE | Frame 0: ice cracking under Tess mid-step on a pond shortcut, parcel flying: 'The shortcut saved four minutes. Then the ice broke.' | Tess controls her breathing, turns toward the direction she came from, kicks and slides out, rolls away and gets to warmth | 52–56 s | Seasonal (first ice). Verified facts (C-2101–2103). The pond kit is reused later in winter content. | M | Second-person instruction title | WS-021-BRIEF | Tess | R-B Real Rule | ESCAPED — Back toward the ice that held her. REAL RULE: Fell through ice? Turn back the way you came. Kick, slide, roll. | K6 pond/ice; K9 | C-2101, C-2102, C-2103; C-2104 not shown unless verified | R08 Cold Water Overboard
22 | 2026-11-21 | Sat | Subway train stopped in a tunnel as the outbreak reaches the rear car: walk the dark tunnel or hold the front car? | The Subway Stopped in the Tunnel. Then the Lights Went Out. | P1 OUTBREAK | Frame 0: emergency-lit subway car stopped in a tunnel; passengers peering into the dark through the front window: 'Somewhere behind them, people started screaming.' | Kai keeps people in the front car behind the latched sliding door the Turned can't open; when power returns the train rolls into the station | 60–64 s | A weekend outbreak in week 4 with new tension (darkness). The heavy kit is scheduled late enough to build in week 2. | H | Darkness and sound-design emphasis (audio-led suspense) | WS-022-BRIEF | Kai | R-A Location Outbreak | SURVIVED — He held the car they couldn't open. | K8 subway car/tunnel (new); K10; K9 | WR-03, WR-04; avoid third-rail claims unless verified | R04 Gas Station
23 | 2026-11-22 | Sun | Wildfire evacuation: one road out of the canyon, and the cost of waiting to pack | Wildfire Evacuation: Why Waiting One More Hour Is Dangerous | P2 REAL RULE | Frame 0: orange sky, ash falling on Owen packing his truck: 'One road out. Time to pack, or time to leave.' | Owen leaves when told rather than when he's ready, and passes the checkpoint before the road closes (pending verified guidance) | 56–60 s | Conditional slot. Wildfire interest is high after recent fires [BK]. It needs verification of C-2301; reserve R01/R02 is ready. | M | Urgency hook in P2 (timer) | WS-023-BRIEF | Owen | R-B Real Rule | ESCAPED — He left when told, not when ready. (REAL RULE pending verification) | K6 canyon road; K2 truck; K9 | C-2301 (BLOCKING) | R02 Six Inches of Water
24 | 2026-11-23 | Mon | Five people in a safe room, one hiding a bite; Mia notices who is cold when everyone else is warm | Five People in a Safe Room. One Was Bitten. | P1 OUTBREAK | Frame 0: a barred basement safe room with five faces in candlelight; T1 'BITE → TURNED: 30–90 MIN': 'One of them was bitten. The clock was already running.' | Suspicion falls on scratched, sweaty Tess (scratches don't transmit). Mia notices Nadia shivering in a warm room (fever). Nadia confesses and asks to be locked in the storage room | 62–66 s | Retrieved evidence for hidden-infected mechanics [R-S24]. A single cheap set. Ensemble attachment before the final week. | L | Social-deduction format with child POV (comments guessing the culprit) | WS-024-BRIEF | Mia (ensemble) | R-G Social deduction | SURVIVED (4) — Mia watched who was cold, not scared. | K4 basement; K9 | WR-01 (fever, scratches don't transmit), WR-09 | R07 Wedding Reception
25 | 2026-11-24 | Tue | Avalanche companion rescue: the rescue team is whoever is standing there | Avalanche: Why Your Friends Are Your Only Rescue | P2 REAL RULE | Frame 0: slope fractures, Tess's friend Jun swept away; a T1 clock starts counting UP from 00:00 | Tess searches immediately (beacon, probe, shovel) instead of going for help, and finds Jun in time (pending verified guidance) | 56–60 s | Ski-season start. Conditional on C-2501 verification; reuses snow assets from Station Zero. | M | Count-up timer (vs Day 2 countdown) | WS-025-BRIEF | Tess | R-D Countdown | SURVIVED — She searched instead of going for help. (REAL RULE pending verification) | K6 snow slope (reuse); K9 | C-2501 (BLOCKING) | R08 Cold Water Overboard
26 | 2026-11-25 | Wed | Outbreak at the airport the day before Thanksgiving: everyone runs for the main doors; Kai moves against the crowd | Zombie Outbreak at the Airport the Day Before Thanksgiving | P1 OUTBREAK | Frame 0: a packed terminal with a departures board full of DELAYED; a surge at security; Kai and Mia with backpacks: 'Then the outbreak reached security.' | The crowd Sphere surges to the jammed main doors (WR-07); Kai takes Mia to an empty gate where an agent lets them through the jet-bridge door and down to a ground-crew van | 62–66 s | The day before Thanksgiving is popularly described as one of the busiest travel days [BK, unverified, so it is not claimed on screen or in the title]. It reuses the Day 6 cabin kit for the parked plane. | M/H (reuses plane kit) | Seasonal timing (day before US Thanksgiving) | WS-026-BRIEF | Kai + Mia | R-A Location Outbreak | ESCAPED — Away from the crowd, not with it. | K8 terminal + jet bridge + plane (reuse); K10; K9 | WR-03, WR-07, WR-04 | R09 Cruise Ship
27 | 2026-11-26 | Thu | Thanksgiving grease / turkey-fryer fire: why water is the wrong instinct | Why You Never Put Water on a Grease Fire | P2 REAL RULE | Frame 0: a backyard fryer flares; a cousin runs at it with a pitcher of water; Owen's hand comes up: 'On Thanksgiving, the most dangerous thing isn't the knife.' | Owen stops the water, cuts the gas and smothers the fire per verified guidance; the Fork shows the water preview as a flare-up without injuries | 48–52 s | US Thanksgiving. Conditional on verifying C-2701 (NFPA/USFA); reserve R01 is ready. | L | Seasonal Real Rule on the holiday itself | WS-027-BRIEF | Owen | R-B Real Rule | SAFE — He cut the heat and smothered it. (REAL RULE pending verification) | K4 backyard/kitchen; K9 | C-2701 (BLOCKING) | R01 Lightning
28 | 2026-11-27 | Fri | Black Friday crowd surge: pressure is the danger; how to stay upright and get out (sensitive; no victims depicted) | Caught in a Crowd Surge: How to Stay on Your Feet | P2 REAL RULE | Frame 0: a dense pre-dawn crowd at store doors; a red pressure Sphere building around Tess: 'The danger wasn't the people. It was the pressure.' | Tess keeps her feet, protects her chest and moves diagonally with the flow to a gap at the edge (pending verified guidance) | 56–60 s | Black Friday. Conditional on verifying C-2801 plus a sensitivity review; reserve R02 is ready. | M (reuses store kit) | Sensitive-topic handling (comment sentiment, corrections) | WS-028-BRIEF | Tess | R-B Real Rule | SAFE — With the crowd, then out of it. (REAL RULE pending verification) | K3 store exterior (reuse); K10 crowd; K9 | C-2801 (BLOCKING) | R02 Six Inches of Water
29 | 2026-11-28 | Sat | Stranded in a blizzard three miles from town: walk for help or stay with the car? Both endings | Stranded in a Blizzard: Walk for Help or Stay in the Car? | P2 REAL RULE | Frame 0: a half-buried car on a rural road at night, with the Fork already split: WALK vs WAIT | Walk: whiteout, they lose the road and are found at dawn with frostbite (LOST). Wait: exhaust pipe cleared, engine run in short bursts, car made visible, plough finds them (SURVIVED), per verified guidance | 66–70 s | Winter weekend. A natural bridge to December's winter theme. Conditional on verifying C-2901. | M | Both Endings on P2 (third Both Endings data point) | WS-029-BRIEF | Kai + Mia | R-C Both Endings | WALK: LOST · WAIT: SURVIVED — Stay with the car. (REAL RULE pending verification) | K2 car + snow road (reuse); K9 | C-2901 (BLOCKING) | R02 Six Inches of Water
30 | 2026-11-29 | Sun | The last bus over the mountain pass before it closes: the cast meets, and each skill matters | The Last Bus Out of the City Before the Pass Closes | P1 OUTBREAK | Frame 0: a snowy bus depot at night; a bus sign 'MOUNTAIN PASS — LAST DEPARTURE'; four figures converging from different directions | Kai spots a passenger with no breath (WR-02 callback); Tess drives when the driver runs; Owen knows the pass; they cross before the gate closes and reach Owen's cabin | 68–72 s | Closes the month by uniting the cast and setting up December's winter season. It rewards returning viewers (callbacks to Days 1, 3, 9) while standing alone. | H | Ensemble + forward hook: subscribers gained and returning viewers in the first days of December | WS-030-BRIEF | Kai, Mia, Tess, Owen | R-A Location Outbreak (ensemble) | SURVIVED — Four strangers, one plan. (Forward line: 'December: The Long Winter.') | K2 bus/road (snow); depot (new); K10; K9 | WR-02, WR-08 | R07 Wedding Reception

## Fallback calendar
Day | Date | Weekday | Episode | Title | Lead | Original slot | Pinned reason
1 | 2026-11-09 | Mon | WS-003 | Everyone Says the Superstore Is the Best Place to Survive | Tess | Day 3 (2026-11-02)
2 | 2026-11-10 | Tue | WS-002 | Your Car Is Sinking. You Have About One Minute. | Owen | Day 2 (2026-11-01)
3 | 2026-11-11 | Wed | WS-004 | Why You Shouldn't Run to the Doorway in an Earthquake | Kai | Day 4 (2026-11-03)
4 | 2026-11-12 | Thu | WS-005 | The Blackout Mistake That's More Dangerous Than the Storm | Owen | Day 5 (2026-11-04)
5 | 2026-11-13 | Fri | WS-006 | A Zombie Outbreak at 35,000 Feet: What Would You Do? | Tess | Day 6 (2026-11-05)
6 | 2026-11-14 | Sat | WS-007 | Roof or Basement? We Played Both Endings | Kai + Mia | Day 7 (2026-11-06)
7 | 2026-11-15 | Sun | WS-008 | Why the Highway Overpass Is the Worst Place in a Tornado | Tess | Day 8 (2026-11-07)
8 | 2026-11-16 | Mon | WS-009 | Zombies Can't Swim. So Why Wasn't the Boat Safe? | Owen | Day 9 (2026-11-08)
9 | 2026-11-17 | Tue | WS-018 | If You See a Flash in the Sky, Don't Go to the Window | Tess | Day 18 (2026-11-17) | Leonid week (if C-1802 verified)
10 | 2026-11-18 | Wed | WS-010 | When the Power Goes Out for Days, This Is What Fails First | Kai + Mia (Owen cameo) | Day 10 (2026-11-09)
11 | 2026-11-19 | Thu | WS-012 | House Fire at 3 A.M.: The One Thing That Buys You Time | Owen | Day 12 (2026-11-11)
12 | 2026-11-20 | Fri | WS-011 | Zombie Outbreak in Your Apartment Building: Go Up or Down? | Tess | Day 11 (2026-11-10)
13 | 2026-11-21 | Sat | WS-015 | The Last Place on Earth Without the Outbreak (Part 1) | Owen | Day 15 (2026-11-14) | Saga Part 1 on a Saturday
14 | 2026-11-22 | Sun | WS-016 | Station Zero Part 2: The Only Weapon Was the Cold | Owen | Day 16 (2026-11-15) | Saga Part 2 on the next day (Sunday)
15 | 2026-11-23 | Mon | WS-013 | Zombie Outbreak in a Movie Theater: Nobody Noticed the Screams | Kai | Day 13 (2026-11-12)
16 | 2026-11-24 | Tue | WS-014 | 7 Days of Warning Before the Outbreak: Stay or Leave? | Tess | Day 14 (2026-11-13)
17 | 2026-11-25 | Wed | WS-026 | Zombie Outbreak at the Airport the Day Before Thanksgiving | Kai + Mia | Day 26 (2026-11-25) | Day before US Thanksgiving
18 | 2026-11-26 | Thu | WS-027 | Why You Never Put Water on a Grease Fire | Owen | Day 27 (2026-11-26) | US Thanksgiving
19 | 2026-11-27 | Fri | WS-028 | Caught in a Crowd Surge: How to Stay on Your Feet | Tess | Day 28 (2026-11-27) | Black Friday
20 | 2026-11-28 | Sat | WS-017 | Caught in a Rip Current? Don't Swim Back to Shore. | Kai | Day 17 (2026-11-16)
21 | 2026-11-29 | Sun | WS-021 | Fell Through the Ice? Turn Back the Way You Came. | Tess | Day 21 (2026-11-20)
22 | 2026-11-30 | Mon | WS-019 | Stuck in an Elevator When the Outbreak Starts | Kai + Mia | Day 19 (2026-11-18)
23 | 2026-12-01 | Tue | WS-020 | What Would a Massive Solar Storm Do to the Power Grid? | Owen | Day 20 (2026-11-19)
24 | 2026-12-02 | Wed | WS-022 | The Subway Stopped in the Tunnel. Then the Lights Went Out. | Kai | Day 22 (2026-11-21)
25 | 2026-12-03 | Thu | WS-023 | Wildfire Evacuation: Why Waiting One More Hour Is Dangerous | Owen | Day 23 (2026-11-22)
26 | 2026-12-04 | Fri | WS-024 | Five People in a Safe Room. One Was Bitten. | Mia (ensemble) | Day 24 (2026-11-23)
27 | 2026-12-05 | Sat | WS-025 | Avalanche: Why Your Friends Are Your Only Rescue | Tess | Day 25 (2026-11-24)
28 | 2026-12-06 | Sun | WS-029 | Stranded in a Blizzard: Walk for Help or Stay in the Car? | Kai + Mia | Day 29 (2026-11-28)
29 | 2026-12-07 | Mon | R04 | The Outbreak Starts While You're Getting Gas at 2 A.M. | Tess (fallback lead) | Reserve R04
30 | 2026-12-08 | Tue | WS-030 | The Last Bus Out of the City Before the Pass Closes | Kai, Mia, Tess, Owen | Day 30 (2026-11-29) | Finale

## Briefs
Day | Date | ID | Title | Pillar | Recipe | Lead | Verdict | Duration | Complexity | Main test | Claims | Reserve | Brief file | Full package
1 | 2026-10-31 | WS-001 | Zombie Outbreak on Halloween: How Do You Tell Who's in Costume? | P1 OUTBREAK | R-A Location Outbreak | Kai + Mia | SURVIVED — He watched their breath, not their costumes. | 60–64 s | H (pre-built before launch) | Diegetic-contradiction hook + planted 'rewatch' details (non-breathing figures in early shots) | C-101, C-102, C-103, C-104 | R04 Gas Station, 2 A.M. (if launch slips past Halloween, Day 1 becomes WS-003) | 18_Daily_Briefs/WS-001_2026-10-31_The-Breath-Test.md | 19_Production_Packages_Days_1-3/WS-001_The-Breath-Test
2 | 2026-11-01 | WS-002 | Your Car Is Sinking. You Have About One Minute. | P2 REAL RULE | R-D Countdown | Owen | ESCAPED — He went for the window, not the door. REAL RULE: Car in water: get out through a side window in the first minute. | 56–60 s | M | Countdown HUD opening in the middle of the event; Real Rule card | C-201, C-202, C-203, C-204, C-205 (BLOCKING order check), C-206, C-207 | R02 Six Inches of Water | 18_Daily_Briefs/WS-002_2026-11-01_About-One-Minute.md | 19_Production_Packages_Days_1-3/WS-002_About-One-Minute
3 | 2026-11-02 | WS-003 | Everyone Says the Superstore Is the Best Place to Survive | P1 OUTBREAK | R-A Location Outbreak | Tess | ESCAPED — The best spot was the one nobody picked. | 58–62 s | H (pre-built before launch) | 'Everyone says…' debate premise: comment volume and shares | C-012, C-013 (Sphere scale), C-102/103 rules (WR-03, WR-07) | R03 Day 12: A Knock on the Hatch | 18_Daily_Briefs/WS-003_2026-11-02_The-Superstore-Myth.md | 19_Production_Packages_Days_1-3/WS-003_The-Superstore-Myth
4 | 2026-11-03 | WS-004 | Why You Shouldn't Run to the Doorway in an Earthquake | P2 REAL RULE | R-B Real Rule | Kai | SAFE — He dropped, covered and held on. REAL RULE: Earthquake: Drop, Cover, Hold On — not the doorway. | 48–52 s | L | Myth-busting hook in P2 (compare with Day 8) | C-401, C-402, C-403, C-404 | R01 Lightning | 18_Daily_Briefs/WS-004_2026-11-03_The-Doorway-Myth.md | —
5 | 2026-11-04 | WS-005 | The Blackout Mistake That's More Dangerous Than the Storm | P2 REAL RULE | R-B Real Rule | Owen | SAFE — He got them into fresh air first. REAL RULE: Never run a generator in a garage. Keep it 20+ ft from the house. | 56–60 s | M | Gas (violet) Sphere comprehension; warning-style hook | C-501, C-502, C-503, C-504, C-506 (BLOCKING: fresh air + call for help); C-505 (BLOCKING if alarms mentioned) | R08 Cold Water Overboard | 18_Daily_Briefs/WS-005_2026-11-04_The-Generator-in-the-Garage.md | —
6 | 2026-11-05 | WS-006 | A Zombie Outbreak at 35,000 Feet: What Would You Do? | P1 OUTBREAK | R-A Location Outbreak | Tess | SURVIVED — She stopped running and built a wall. | 62–66 s | H | 'What would you do?' question title; confined-space story | C-102, C-103 (WR-04 push vs climb) | R09 Cruise Ship, Day 3 | 18_Daily_Briefs/WS-006_2026-11-05_Row-31.md | —
7 | 2026-11-06 | WS-007 | Roof or Basement? We Played Both Endings | P1 OUTBREAK | R-C Both Endings | Kai + Mia | ROOF: SURVIVED · BASEMENT: TRAPPED — Pick the place they can't climb to. | 68–72 s | M | Both Endings format baseline (retention through the 'rewind') | C-103 (WR-04), WR-03 | R06 Your First Move (three endings) | 18_Daily_Briefs/WS-007_2026-11-06_Roof-or-Basement-Both-Endings.md | —
8 | 2026-11-07 | WS-008 | Why the Highway Overpass Is the Worst Place in a Tornado | P2 REAL RULE | R-B Real Rule | Tess | SURVIVED — Lower than the road, not under it. REAL RULE: Tornado: never shelter under a highway overpass. | 54–58 s | M | Second myth-busting P2 (compare with Day 4); red wind Sphere | C-801, C-802 (confirm wording), C-803, C-804 | R02 Six Inches of Water | 18_Daily_Briefs/WS-008_2026-11-07_The-Overpass.md | —
9 | 2026-11-08 | WS-009 | Zombies Can't Swim. So Why Wasn't the Boat Safe? | P1 OUTBREAK | R-A Location Outbreak | Owen | ESCAPED — He checked the tide, not just the distance. | 58–62 s | M | World-rule payoff twist (WR-02 callback from Day 1) | C-102 (WR-02), WR-04 | R03 Bunker Hatch | 18_Daily_Briefs/WS-009_2026-11-08_They-Cant-Swim.md | —
10 | 2026-11-09 | WS-010 | When the Power Goes Out for Days, This Is What Fails First | P3 WORLD SHIFT | R-E World Shift ladder | Kai + Mia (Owen cameo) | SAFE — They planned by the hour, not the day. REAL RULE: Fridge about 4 h; full freezer about 48 h. Keep the doors shut. | 62–66 s | M | Hour-by-hour ladder format (P3 baseline) | C-1001, C-1002, C-011, C-022, C-501/502; C-1003 must be cut or verified | R08 Cold Water Overboard | 18_Daily_Briefs/WS-010_2026-11-09_What-Fails-First.md | —
11 | 2026-11-10 | WS-011 | Zombie Outbreak in Your Apartment Building: Go Up or Down? | P1 OUTBREAK | R-A Location Outbreak | Tess | SURVIVED — She let the stairwell door do the work. | 58–62 s | M | Up-vs-down debate premise ([R-S38] evidence) | C-103 (WR-04); C-1101 (in-story fact only) | R04 Gas Station | 18_Daily_Briefs/WS-011_2026-11-10_Floor-14.md | —
12 | 2026-11-11 | WS-012 | House Fire at 3 A.M.: The One Thing That Buys You Time | P2 REAL RULE | R-B Real Rule | Owen | SAFE — His door was closed before the fire started. REAL RULE: Sleep with the door closed. Get out, stay out. | 54–58 s | M | Split-screen comparison opener | C-1201, C-1202, C-1203, C-1204, C-1206 (BLOCKING: window as second way out); C-1205 only if verified | R01 Lightning | 18_Daily_Briefs/WS-012_2026-11-11_Close-the-Door.md | —
13 | 2026-11-12 | WS-013 | Zombie Outbreak in a Movie Theater: Nobody Noticed the Screams | P1 OUTBREAK | R-A Location Outbreak | Kai | ESCAPED — He picked the door that opens one way. | 58–62 s | M | Comedic-irony hook | WR-03, WR-04; C-1101 (in-story only) | R07 Wedding Reception | 18_Daily_Briefs/WS-013_2026-11-12_The-Loudest-Room-in-Town.md | —
14 | 2026-11-13 | WS-014 | 7 Days of Warning Before the Outbreak: Stay or Leave? | P3 WORLD SHIFT | R-C Both Endings | Tess | STAY: TRAPPED · LEAVE EARLY: SURVIVED — Leaving early beats leaving fast. | 68–72 s | M | Both Endings on a P3 premise (second data point) | C-1401 (qualified), C-1002, WR-08 | R06 Your First Move | 18_Daily_Briefs/WS-014_2026-11-13_Seven-Days-of-Warning-Both-Endings.md | —
15 | 2026-11-14 | WS-015 | The Last Place on Earth Without the Outbreak (Part 1) | P1 OUTBREAK (SAGA) | R-F Two-part Saga | Owen | SURVIVED — Owen read the bandage, not the smile. (Forward line: 'The heat runs out in 30 hours.') | 66–70 s | H | SAGA Part 1: does a resolved Part 1 with a forward line lift Part 2 views and follows? | WR-01 (fever, bite), WR-04; C-1501 (no real numbers unless verified) | R05 The Crossing (original puzzle) | 18_Daily_Briefs/WS-015_2026-11-14_Station-Zero-Part-1.md | —
16 | 2026-11-15 | WS-016 | Station Zero Part 2: The Only Weapon Was the Cold | P1 OUTBREAK (SAGA) | R-F Two-part Saga | Owen | SURVIVED — He turned the cold into a wall. | 66–70 s | M (reuses Part 1) | SAGA Part 2: retention of cold viewers; Part2/Part1 view ratio | WR-06; WR-02 (frost/no breath); C-1501 | R03 Bunker Hatch | 18_Daily_Briefs/WS-016_2026-11-15_Station-Zero-Part-2.md | —
17 | 2026-11-16 | WS-017 | Caught in a Rip Current? Don't Swim Back to Shore. | P2 REAL RULE | R-B Real Rule | Kai | SAFE — He swam sideways, not against it. REAL RULE: Rip current: don't fight it. Float, then swim parallel to shore. | 50–54 s | M | Water Sphere + swimmer POV; Real Rule after the saga weekend | C-1701, C-1702, C-1703; C-1704 not animated unless verified | R08 Cold Water Overboard | 18_Daily_Briefs/WS-017_2026-11-16_Dont-Swim-Back.md | —
18 | 2026-11-17 | WS-018 | If You See a Flash in the Sky, Don't Go to the Window | P2 REAL RULE | R-B Real Rule | Tess | SAFE — Away from the glass, not toward it. REAL RULE (pending verification): A bright flash in the sky? Stay away from windows. | 52–56 s | M | Historical-reference hook ('In 2013…') in Leonid week | C-1801 (BLOCKING), C-1802 (BLOCKING) | R01 Lightning (verified) | 18_Daily_Briefs/WS-018_2026-11-17_The-Flash-Before-the-Bang.md | —
19 | 2026-11-18 | WS-019 | Stuck in an Elevator When the Outbreak Starts | P1 OUTBREAK | R-A Location Outbreak | Kai + Mia | SURVIVED — They stayed in the box nobody could open. REAL RULE: Stuck in an elevator? Stay in, use the alarm, don't force the doors. | 52–56 s | L | Low-cost single-set episode: performance vs production cost | C-1901, C-1902, WR-03, WR-04 | R04 Gas Station | 18_Daily_Briefs/WS-019_2026-11-18_Between-Floors.md | —
20 | 2026-11-19 | WS-020 | What Would a Massive Solar Storm Do to the Power Grid? | P3 WORLD SHIFT | R-E World Shift ladder | Owen | SAFE — The lights were a warning, not a show. | 60–64 s | M | Spectacle visual (aurora) hook in P3 | C-2001 (BLOCKING), C-1001, C-1002 | R01 Lightning | 18_Daily_Briefs/WS-020_2026-11-19_The-Night-the-Sky-Turned-Green.md | —
21 | 2026-11-20 | WS-021 | Fell Through the Ice? Turn Back the Way You Came. | P2 REAL RULE | R-B Real Rule | Tess | ESCAPED — Back toward the ice that held her. REAL RULE: Fell through ice? Turn back the way you came. Kick, slide, roll. | 52–56 s | M | Second-person instruction title | C-2101, C-2102, C-2103; C-2104 not shown unless verified | R08 Cold Water Overboard | 18_Daily_Briefs/WS-021_2026-11-20_Turn-Back-the-Way-You-Came.md | —
22 | 2026-11-21 | WS-022 | The Subway Stopped in the Tunnel. Then the Lights Went Out. | P1 OUTBREAK | R-A Location Outbreak | Kai | SURVIVED — He held the car they couldn't open. | 60–64 s | H | Darkness and sound-design emphasis (audio-led suspense) | WR-03, WR-04; avoid third-rail claims unless verified | R04 Gas Station | 18_Daily_Briefs/WS-022_2026-11-21_Tunnel-9.md | —
23 | 2026-11-22 | WS-023 | Wildfire Evacuation: Why Waiting One More Hour Is Dangerous | P2 REAL RULE | R-B Real Rule | Owen | ESCAPED — He left when told, not when ready. (REAL RULE pending verification) | 56–60 s | M | Urgency hook in P2 (timer) | C-2301 (BLOCKING) | R02 Six Inches of Water | 18_Daily_Briefs/WS-023_2026-11-22_One-Road-Out.md | —
24 | 2026-11-23 | WS-024 | Five People in a Safe Room. One Was Bitten. | P1 OUTBREAK | R-G Social deduction | Mia (ensemble) | SURVIVED (4) — Mia watched who was cold, not scared. | 62–66 s | L | Social-deduction format with child POV (comments guessing the culprit) | WR-01 (fever, scratches don't transmit), WR-09 | R07 Wedding Reception | 18_Daily_Briefs/WS-024_2026-11-23_Five-in-the-Safe-Room.md | —
25 | 2026-11-24 | WS-025 | Avalanche: Why Your Friends Are Your Only Rescue | P2 REAL RULE | R-D Countdown | Tess | SURVIVED — She searched instead of going for help. (REAL RULE pending verification) | 56–60 s | M | Count-up timer (vs Day 2 countdown) | C-2501 (BLOCKING) | R08 Cold Water Overboard | 18_Daily_Briefs/WS-025_2026-11-24_Fifteen-Minutes.md | —
26 | 2026-11-25 | WS-026 | Zombie Outbreak at the Airport the Day Before Thanksgiving | P1 OUTBREAK | R-A Location Outbreak | Kai + Mia | ESCAPED — Away from the crowd, not with it. | 62–66 s | M/H (reuses plane kit) | Seasonal timing (day before US Thanksgiving) | WR-03, WR-07, WR-04 | R09 Cruise Ship | 18_Daily_Briefs/WS-026_2026-11-25_Gate-22.md | —
27 | 2026-11-26 | WS-027 | Why You Never Put Water on a Grease Fire | P2 REAL RULE | R-B Real Rule | Owen | SAFE — He cut the heat and smothered it. (REAL RULE pending verification) | 48–52 s | L | Seasonal Real Rule on the holiday itself | C-2701 (BLOCKING) | R01 Lightning | 18_Daily_Briefs/WS-027_2026-11-26_Never-Water.md | —
28 | 2026-11-27 | WS-028 | Caught in a Crowd Surge: How to Stay on Your Feet | P2 REAL RULE | R-B Real Rule | Tess | SAFE — With the crowd, then out of it. (REAL RULE pending verification) | 56–60 s | M (reuses store kit) | Sensitive-topic handling (comment sentiment, corrections) | C-2801 (BLOCKING) | R02 Six Inches of Water | 18_Daily_Briefs/WS-028_2026-11-27_The-Surge.md | —
29 | 2026-11-28 | WS-029 | Stranded in a Blizzard: Walk for Help or Stay in the Car? | P2 REAL RULE | R-C Both Endings | Kai + Mia | WALK: LOST · WAIT: SURVIVED — Stay with the car. (REAL RULE pending verification) | 66–70 s | M | Both Endings on P2 (third Both Endings data point) | C-2901 (BLOCKING) | R02 Six Inches of Water | 18_Daily_Briefs/WS-029_2026-11-28_Walk-or-Wait-Both-Endings.md | —
30 | 2026-11-29 | WS-030 | The Last Bus Out of the City Before the Pass Closes | P1 OUTBREAK | R-A Location Outbreak (ensemble) | Kai, Mia, Tess, Owen | SURVIVED — Four strangers, one plan. (Forward line: 'December: The Long Winter.') | 68–72 s | H | Ensemble + forward hook: subscribers gained and returning viewers in the first days of December | WR-02, WR-08 | R07 Wedding Reception | 18_Daily_Briefs/WS-030_2026-11-29_The-Last-Bus-Out.md | —

## Reserves
ID | Topic | Pillar | Title | Claims | Replaces | Spine
R01 | Lightning on a hike: the picnic shelter won't save you; crouching doesn't either | P2 | Why the Picnic Shelter Won't Save You From Lightning | C-R101–R104 (verified) | Any P2 slot that fails verification (WS-018, WS-023, WS-027) | Tess hikes; thunder; hikers huddle under a picnic shelter. FORK: SHELTER vs RUN TO THE CAR. She reaches her hard-topped car (metal shell, not tyres) and waits 30 minutes after the last thunder.
R02 | Flash flood: six inches of water and the dip in the road | P2 | Six Inches of Water: The Flash Flood Mistake | C-R201–R204 (verified) | WS-023 / WS-028 / WS-029 if blocked | Owen at a flooded low-water crossing at night. FORK: DRIVE THROUGH vs TURN AROUND. The preview shows the car floating at bumper height; he reverses.
R03 | Day 12 in the bunker: a knock on the hatch | P1 | Day 12 in the Bunker. Then Someone Knocked. | WR-01–WR-04 | Any P1 slot | Tess in a prepper bunker; rhythmic knocking. The Turned don't knock in rhythm (they push). FORK: OPEN vs PERISCOPE CHECK. It's Owen.
R04 | Gas station at 2 a.m.: fuel, snacks and one locked bathroom | P1 | The Outbreak Starts While You're Getting Gas at 2 A.M. | WR-03/WR-04 | Any P1 slot; the cheapest P1 (one set); Day-1 fallback if launch slips | Kai refuels; the clerk is locked in; something is in the bathroom. FORK: FILL THE TANK vs LEAVE ON A QUARTER TANK. The fuel nozzle's click is the loudest sound for miles.
R05 | The Crossing: an original timed puzzle (three survivors, one boat, one turned dog cage) | P1 | Can You Get Everyone Across Before Sunrise? | Fiction | WS-015/016 if saga assets slip | An original river-crossing logic puzzle with a viewer pause beat (not TED-Ed's bridge riddle).
R06 | Your first move: fortify, flee or find a group? Three endings | P3 | Zombie Outbreak: Fortify, Flee or Find a Group? | WR set | Any Both Endings slot | Three-panel Fork; each ending runs about 18 s; the Verdict compares them.
R07 | Wedding reception: the best man was bitten at the bachelor party | P1 | The Best Man Was Bitten at the Bachelor Party | WR-01 | Any P1 slot (dark comedy) | Tess is a guest; the toast; the best man's fever. FORK: STOP THE TOAST vs CLEAR THE DANCE FLOOR.
R08 | Cold water overboard: the gasp comes first | P2 | Fell Into Cold Water? The First Minute Isn't About the Cold | C-2101/2102 (verified) | Any P2 slot | Owen falls off a dock in November. He controls the gasp and keeps his face up; 1-10-1 timer.
R09 | Cruise ship: one sick passenger, four days from port | P1 | Zombie Outbreak on a Cruise Ship, Four Days From Port | WR set | WS-006 / WS-026 | Kai and Mia on deck 9. FORK: CABIN vs LIFEBOAT STATION.
R10 | Hurricane: the calm in the eye | P2 | The Hurricane Went Quiet. That Was the Trap. | Needs verification (NOAA/NWS) | Next season, or after verification | Owen; the eye passes; neighbours go outside. FORK: GO OUT vs STAY IN.

## Topic pool
ID | Premise | Pillar | Evidence of interest / factual support | Season/trend | AR | HC | SS | VP | OR | PO | EC | CF | PF | Weighted score /100 | Decision | Reason / note
T001 | Outbreak on a remote farm: livestock noise, generator, barn | P1 | [R] TikTok topic pages 'farmer in zombie apocalypse pt3' (appendix A/C); [R-S36] Cornell rural logic | E | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 5 | 4 | 76.1 | REJ | Reference territory ('The Last Farm'); any farm story would read as a copy
T002 | City vs countryside: Hour 0 downtown, reach low-density land before bridges close | P1 | [R-S36][R-S37] Cornell model coverage | E | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 5 | 3 | 78.0 | DEF | Strong evidence; heavy map/crowd work. Month 2 candidate (overlaps WS-014)
T003 | High-rise: floor 2 or floor 30? Stairwell-door logic | P1 | [R-S38] viewer hiding debate | E | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 87.8 | WS-011 | Selected
T004 | School lockdown turns into outbreak | P1 | [R-S30] Snapchat precedent | E | 4 | 4 | 4 | 4 | 2 | 3 | 3 | 3 | 3 | 68.3 | REJ | Sensitivity: real school-violence associations; not brand-safe
T005 | Waking alone in a hospital on day 9 | P1 | [J] | E | 3 | 4 | 3 | 3 | 1 | 3 | 1 | 4 | 3 | 58.0 | REJ | Derivative of well-known film/TV openings
T006 | Shopping mall stronghold: glass doors and food court | P1 | [BK] classic debate | E | 4 | 4 | 3 | 4 | 2 | 3 | 2 | 4 | 3 | 66.3 | REJ | Overlaps superstore (WS-003) with weaker angle; film-derivative
T007 | Warehouse superstore: 'best place to survive?' — the crowd problem and the delivery van | P1 | [BK] common 'Costco in the apocalypse' debate | E | 5 | 5 | 4 | 4 | 4 | 5 | 3 | 5 | 3 | 86.8 | WS-003 | Selected; debate magnet
T008 | Hardware store vs superstore poll | P1 | [BK] | E | 3 | 4 | 2 | 3 | 3 | 2 | 2 | 4 | 4 | 60.5 | REJ | Poll, not a story
T009 | Prison: walls perfect, who's inside? | P1 | [BK] | E | 3 | 4 | 3 | 3 | 1 | 3 | 2 | 4 | 2 | 57.6 | REJ | Derivative of TV prison arc; heavy sets
T010 | Sailboat: 'they can't swim' — but they don't breathe (anchor chain) | P1 | [BK] boat strategy in popular survival guides | E | 4 | 5 | 4 | 4 | 5 | 5 | 3 | 5 | 3 | 85.9 | WS-009 | Selected; pays off WR-02
T011 | Small island safe until the ferry arrives | P1 | [BK] | E | 3 | 4 | 3 | 4 | 3 | 3 | 2 | 4 | 3 | 65.4 | DEF | Overlaps WS-009 water theme; month 2
T012 | Cruise ship: one sick passenger, four days from port | P1 | [J][BK] cruise outbreak news | E | 4 | 4 | 4 | 4 | 3 | 4 | 2 | 4 | 2 | 71.2 | R09 | Reserve (heavy kit)
T013 | Airplane at 35,000 ft: row 31 was bitten | P1 | [J] | E (holiday travel) | 5 | 5 | 5 | 4 | 3 | 4 | 2 | 5 | 2 | 81.5 | WS-006 | Selected; strong confined-space premise
T014 | Subway car stalls in a tunnel, lights out | P1 | [J] | E | 4 | 5 | 4 | 4 | 3 | 4 | 2 | 5 | 3 | 78.0 | WS-022 | Selected
T015 | Gas station at 2 a.m.: fuel, snacks, one locked bathroom | P1 | [J] | E | 4 | 4 | 4 | 3 | 4 | 4 | 2 | 5 | 5 | 79.0 | R04 | Reserve; cheapest P1 (one set)
T016 | Ski lodge snowed in: are they slower in the cold? | P1 | [J] | W | 3 | 4 | 3 | 4 | 3 | 3 | 1 | 4 | 3 | 63.9 | DEF | Cold rule handled by Station Zero saga
T017 | Thanksgiving dinner: grandpa 'isn't feeling well' | P1 | [J] + calendar | T | 4 | 5 | 4 | 3 | 4 | 4 | 2 | 4 | 4 | 78.0 | DEF | Strong but Thanksgiving slot goes to grease-fire Real Rule; keep for Thanksgiving 2027 or a 'Both Endings'
T018 | Black Friday doorbuster: the crowd isn't shoppers | P1 | [J] + calendar | T | 4 | 5 | 3 | 4 | 3 | 3 | 2 | 4 | 2 | 69.3 | DEF | Black Friday slot used for crowd-surge Real Rule
T019 | Halloween: everyone is in zombie makeup — the breath test | P1 | [J] + calendar (Sat 31 Oct) + [R-S11][R-S43][R-S48] October zombie scheduling precedents | H | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 5 | 3 | 93.2 | WS-001 | Selected Day 1
T020 | Trick-or-treat route: houses with lights on are dangerous | P1 | [J] | H | 3 | 4 | 3 | 4 | 3 | 3 | 1 | 4 | 3 | 63.9 | REJ | Folded into WS-001
T021 | Wedding reception: the best man was bitten at the bachelor party | P1 | [J] | E | 4 | 5 | 4 | 4 | 4 | 4 | 2 | 4 | 3 | 78.0 | R07 | Reserve; dark comedy
T022 | Office tower Monday: badge doors lock | P1 | [J] | E | 3 | 4 | 3 | 3 | 3 | 3 | 1 | 4 | 3 | 62.0 | REJ | Rests on unverified access-control claims (fail-safe vs fail-secure)
T023 | Fast-food kitchen: walk-in freezer panic room | P1 | [R-S30] Snapchat precedent | E | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 69.8 | DEF | Freezer logic conflicts with WR-06 only below −20 °C; month 2
T024 | Submarine: surface or stay down 90 days? | P1 | [J] | E | 3 | 4 | 4 | 3 | 4 | 3 | 1 | 3 | 2 | 62.4 | REJ | Niche; expensive; little viewer relevance
T025 | Antarctic station: the last plane brings it (2-part saga) | P1 | [J] | W (southern summer) | 4 | 5 | 5 | 5 | 4 | 5 | 2 | 5 | 2 | 84.9 | WS-015/016 | Selected as the saga test
T026 | Theme park after closing | P1 | [J] | E | 3 | 4 | 3 | 4 | 2 | 3 | 1 | 4 | 2 | 60.0 | REJ | Film-derivative; heavy
T027 | Zoo outbreak: are animals infected? | P1 | [R-S51] film 'Zombies im Zoo' exists | E | 3 | 4 | 3 | 4 | 2 | 3 | 3 | 3 | 2 | 61.0 | REJ | Existing film; animal-infection rules would complicate WR set
T028 | Movie theater: the screams aren't from the film | P1 | [J] | H/E | 4 | 5 | 4 | 4 | 4 | 4 | 2 | 5 | 3 | 80.0 | WS-013 | Selected
T029 | Stadium: 70,000 people, 12 exits | P1 | [J] | E | 3 | 4 | 3 | 4 | 3 | 3 | 1 | 4 | 1 | 60.0 | REJ | Crowd-heavy; overlaps WS-028
T030 | Highway gridlock: abandon the car or wait? | P1 | [J]; [R-S36–S39] spread critique | E | 4 | 4 | 3 | 4 | 3 | 3 | 2 | 4 | 3 | 68.3 | DEF | Overlaps WS-029 'walk or wait'
T031 | Prepper bunker: a knock on the hatch on day 12 | P1 | [R-S38] bunker choice in hiding debate; [R-S49] | E | 4 | 5 | 4 | 3 | 4 | 4 | 4 | 5 | 5 | 84.9 | R03 | Reserve; very cheap single set
T032 | Space station crew watches from orbit | P1 | [J] | S | 3 | 4 | 3 | 4 | 4 | 3 | 1 | 3 | 2 | 62.0 | REJ | Weak relevance; expensive
T033 | Remote lighthouse/cabin: one road in | P1 | [J] | E | 3 | 3 | 3 | 4 | 3 | 3 | 1 | 4 | 3 | 61.0 | DEF | Folded into December 'Long Winter' bridge
T034 | Elevator between floors as it begins | P1 | [J]; real elevator facts [LEDGER C-1901/1902] | E | 4 | 5 | 4 | 3 | 4 | 4 | 3 | 5 | 5 | 83.4 | WS-019 | Selected; cheap
T035 | Quarantine checkpoint: scanner says you're infected | P1 | [J] | E | 3 | 4 | 4 | 3 | 2 | 3 | 1 | 4 | 3 | 62.4 | REJ | Derivative of a famous game/TV setting
T036 | Gym: strongest people, weakest (glass) walls | P1 | [J] | Jan | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 4 | 3 | 59.0 | DEF | Seasonal for January
T037 | Timed crossing puzzle: 4 survivors, 17 minutes (TED-Ed-style) | P1 | [R-S15/16] TED-Ed bridge riddle ~24M plays | E | 5 | 5 | 4 | 3 | 1 | 4 | 5 | 4 | 4 | 79.5 | R05 | Reserve ONLY as an original puzzle mechanic (not the bridge-and-torch riddle)
T038 | Your first move: fortify, flee or find a group (three endings) | P3 | [R-S32/33] an existing Short asks exactly this | E | 5 | 5 | 3 | 3 | 3 | 4 | 4 | 5 | 4 | 81.5 | R06 | Reserve (three-ending variant of Both Endings)
T039 | Seven days of warning: leave the city or lock down? (Both Endings) | P3 | [R-S29] 'TikTok-viral' advance-warning story; [R-S36] Cornell model | E | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 84.9 | WS-014 | Selected
T040 | You vs a 1,000-zombie horde | P1 | [R-S12] title exists | E | 4 | 4 | 2 | 4 | 1 | 2 | 3 | 2 | 2 | 55.1 | REJ | Combat/numbers spectacle; off-brand; derivative title
T041 | Would you survive? five questions to day 30 | P1 | [R-S11][R-S32][R-S42] recurring formula | E | 4 | 4 | 2 | 3 | 2 | 3 | 4 | 4 | 4 | 66.8 | DEF | Quiz format; test in month 2
T042 | Hidden infected: one of five in the safe room was bitten (Mia's POV) | P1 | [R-S24] ErrorMotion hidden-infected hits | E | 4 | 5 | 5 | 3 | 4 | 5 | 4 | 5 | 5 | 89.8 | WS-024 | Selected
T043 | How an outbreak could plausibly start (science) | P3 | [R-S34/35] AsapSCIENCE coverage; [R-S40] hoax risk | E | 3 | 4 | 2 | 3 | 2 | 2 | 3 | 2 | 4 | 56.1 | REJ | Science-explainer drift + hoax risk
T044 | Fungal spores, no bites | P1 | [BK] post-2023 interest | S | 3 | 4 | 3 | 4 | 1 | 3 | 2 | 3 | 3 | 59.5 | REJ | Strong association with an existing franchise
T045 | Permafrost 'zombie virus' | P3 | [BK] news | S | 3 | 4 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 52.7 | REJ | Health-hoax risk
T046 | Outbreak on Leonid night | P1 | [J] | L | 3 | 4 | 3 | 4 | 3 | 3 | 1 | 4 | 3 | 63.9 | REJ | Would link a harmless meteor shower to danger
T047 | The night clocks fall back: dark at 5 p.m. | P1 | [J] | D | 2 | 3 | 2 | 3 | 3 | 2 | 1 | 3 | 4 | 51.2 | REJ | Weak premise; used as atmosphere in WS-002 instead
T048 | Blizzard + zombies: do they freeze? | P1 | [J] | W | 3 | 4 | 3 | 4 | 3 | 3 | 1 | 4 | 3 | 63.9 | REJ | Covered by Station Zero (WR-06)
T049 | Day 1,000: what the world looks like after 3 years | P3 | [J] decay-genre [BK] | E | 4 | 4 | 2 | 5 | 3 | 3 | 1 | 3 | 2 | 62.4 | DEF | World-building; month 2 test
T050 | Keep the barking dog or not? | P1 | [J] | E | 3 | 4 | 3 | 3 | 1 | 3 | 1 | 3 | 4 | 58.0 | REJ | Reference territory (Rusty)
T051 | Earthquake: why the doorway is a trap | P2 | [BK] recurring myth corrections; [LEDGER C-401–404] | S/E | 5 | 5 | 4 | 4 | 3 | 4 | 4 | 5 | 5 | 87.8 | WS-004 | Selected
T052 | Tornado on the highway: why the overpass is a death trap | P2 | [BK]; [LEDGER C-801–804] | Spring/Nov | 4 | 5 | 4 | 5 | 3 | 4 | 4 | 5 | 3 | 82.9 | WS-008 | Selected
T053 | Flash flood: six inches of water | P2 | [BK]; [LEDGER C-R201–204] | S/E | 4 | 5 | 4 | 4 | 3 | 4 | 4 | 5 | 4 | 82.9 | R02 | Reserve (verified)
T054 | Tsunami: the ocean pulls back | P2 | [BK] 2025 warnings | S | 4 | 5 | 4 | 5 | 3 | 4 | 2 | 5 | 3 | 80.0 | DEF | Facts unverified; month 2 after verification
T055 | Wildfire evacuation with one road out | P2 | [BK] 2025 LA fires; [LEDGER-BLOCK C-2301] | S | 4 | 5 | 4 | 5 | 3 | 4 | 2 | 5 | 3 | 80.0 | WS-023 | Selected, conditional on verification (reserve R01/R02)
T056 | Blizzard: stranded overnight — walk or wait? (Both Endings) | P2 | [BK]; [LEDGER-BLOCK C-2901] | W | 4 | 5 | 4 | 4 | 4 | 4 | 2 | 5 | 4 | 82.0 | WS-029 | Selected, conditional on verification
T057 | Avalanche: the first 15 minutes | P2 | [BK]; [LEDGER-BLOCK C-2501] | W | 3 | 5 | 4 | 5 | 3 | 4 | 2 | 5 | 3 | 77.1 | WS-025 | Selected, conditional on verification
T058 | Hurricane: the calm in the eye | P2 | [BK] | Jun–Nov | 4 | 4 | 4 | 4 | 3 | 4 | 2 | 5 | 3 | 75.1 | R10 | Reserve (verify first)
T059 | Heat wave + power outage on the top floor | P2 | [BK] | Summer | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 4 | 4 | 68.3 | DEF | Seasonal (June)
T060 | Volcanic ash 30 km away: what actually kills | P2 | [BK] | S | 3 | 4 | 3 | 4 | 3 | 3 | 1 | 4 | 3 | 63.9 | DEF | Unverified; doom-bait risk
T061 | Solar superstorm: the night the sky turned green | P3 | [BK] May 2024 G5; [LEDGER-BLOCK C-2001] | S | 4 | 5 | 4 | 5 | 4 | 4 | 2 | 5 | 3 | 82.0 | WS-020 | Selected, conditional on verification
T062 | Nuclear alert: 15 minutes to get inside | P2 | [BK] 2018 false alert | S | 4 | 5 | 4 | 4 | 3 | 4 | 1 | 4 | 3 | 74.6 | DEF | High-stakes facts unverified; sensitive
T063 | Sinking car: about one minute | P2 | [BK]; [LEDGER C-201–206] | E | 5 | 5 | 5 | 5 | 3 | 5 | 4 | 5 | 4 | 92.7 | WS-002 | Selected Day 2
T064 | House fire at 3 a.m.: close the door | P2 | [BK] UL campaign; [LEDGER C-1201–1204] | W | 5 | 5 | 4 | 4 | 3 | 4 | 4 | 5 | 4 | 85.9 | WS-012 | Selected
T065 | Rip current: don't swim back | P2 | [BK]; [LEDGER C-1701–1703] | Summer/E | 4 | 5 | 4 | 4 | 3 | 4 | 4 | 5 | 4 | 82.9 | WS-017 | Selected
T066 | Lost in the woods at dusk: stay put | P2 | [BK] Hug-a-Tree | Fall | 4 | 4 | 3 | 4 | 3 | 3 | 2 | 4 | 4 | 70.2 | DEF | Facts unverified; month 2
T067 | Stuck in an elevator (real): don't pry the doors | P2 | [LEDGER C-1901/1902] | E | 3 | 4 | 2 | 3 | 3 | 3 | 4 | 4 | 5 | 67.8 | REJ | Merged into WS-019 outbreak version
T068 | The generator in the garage (CO during a blackout) | P2 | [BK] CDC post-storm warnings; [LEDGER C-501–504] | W | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 87.8 | WS-005 | Selected
T069 | Bear encounter: black vs brown | P2 | [BK] 2024 'man vs bear' debate | E | 4 | 5 | 3 | 4 | 3 | 3 | 2 | 4 | 3 | 71.2 | DEF | Facts unverified
T070 | Falling through ice: turn back the way you came | P2 | [BK]; [LEDGER C-2101–2103] | W | 4 | 5 | 4 | 4 | 3 | 4 | 4 | 5 | 4 | 82.9 | WS-021 | Selected
T071 | Turkey-fryer fire on Thanksgiving | P2 | [BK] NFPA peak-day claim (verify); [LEDGER-BLOCK C-2701] | T | 4 | 5 | 3 | 4 | 3 | 4 | 2 | 4 | 4 | 75.6 | WS-027 | Selected, conditional on verification
T072 | Black Friday crowd surge: stay on your feet | P2 | [BK]; [LEDGER-BLOCK C-2801] | T | 4 | 5 | 4 | 4 | 3 | 4 | 2 | 4 | 3 | 76.1 | WS-028 | Selected, conditional on verification + sensitivity review
T073 | City-killer asteroid with years of warning | P3 | [R-S23] What If award entry | S | 4 | 4 | 3 | 5 | 2 | 3 | 3 | 3 | 2 | 65.9 | DEF | Facts unverified; competitor-dense
T074 | Plane ditching on water: brace, bags, vest outside | P2 | [BK] | E | 4 | 4 | 4 | 4 | 3 | 4 | 1 | 4 | 2 | 69.8 | DEF | Unverified; overlaps WS-006 cabin kit — month 2
T075 | Lost at sea in a life raft | P2 | [BK] | E | 3 | 4 | 3 | 4 | 3 | 3 | 1 | 4 | 3 | 63.9 | DEF | Unverified
T076 | Real historical disaster retold minute by minute | P2 | [R-S2/S3] Zack D. Films' top videos are real incidents | E | 5 | 5 | 4 | 4 | 2 | 4 | 4 | 3 | 3 | 78.0 | DEF | Promising (evidence) but needs a respectful historical format and verification; month 2 test
T077 | Three myths that get people killed (doorway, overpass, 'a little water') | P2 | [BK] | E | 4 | 5 | 2 | 3 | 2 | 3 | 3 | 4 | 4 | 68.3 | DEF | Listicle; the individual episodes cover them
T078 | Winter myths: eat snow, alcohol warms you | P2 | [BK] | W | 3 | 4 | 2 | 3 | 3 | 2 | 1 | 4 | 4 | 59.0 | DEF | Unverified
T079 | 'Play dead' works for one bear, not the other | P2 | [BK] | E | 3 | 4 | 3 | 3 | 3 | 3 | 1 | 4 | 4 | 63.9 | DEF | Unverified
T080 | Zombie-movie rules that would get you killed | P1 | [J][R-S36–39] | H/E | 4 | 4 | 2 | 3 | 2 | 3 | 2 | 4 | 4 | 63.9 | DEF | Listicle; month 2
T081 | Movie quicksand vs real quicksand | P2 | [BK] | E | 2 | 3 | 2 | 3 | 2 | 2 | 1 | 2 | 4 | 47.3 | REJ | Low stakes; unverified
T082 | A stranger at the door on day 5: let them in? | P1 | [J] | E | 4 | 5 | 4 | 3 | 2 | 4 | 1 | 4 | 5 | 74.6 | REJ | Too close to the reference's Part 2 trust dilemma
T083 | Your friend hides a bite: tell the group? | P1 | [J][R-S24] | E | 4 | 5 | 4 | 3 | 3 | 4 | 2 | 4 | 5 | 78.0 | REJ | Folded into WS-024
T084 | Pick 3 items from a 12-item grid | P3 | [J] | E | 3 | 4 | 1 | 2 | 2 | 2 | 1 | 3 | 5 | 52.7 | REJ | Not a story
T085 | Roof or basement? We played both endings (house outbreak) | P1 | [R-S38] hiding debate (up vs down) | E | 5 | 5 | 4 | 4 | 4 | 5 | 4 | 5 | 4 | 90.2 | WS-007 | Selected; Both Endings format test
T086 | Grid down: what fails first in your home, hour by hour | P3 | [BK] Iberian blackout 2025; [LEDGER C-1001/1002/011] | S/W | 4 | 5 | 3 | 4 | 3 | 4 | 3 | 5 | 4 | 79.0 | WS-010 | Selected (unverified items cut unless verified)
T087 | The flash before the bang: why you don't go to the window (Chelyabinsk 2013) | P2 | [BK]; [LEDGER-BLOCK C-1801/1802] | L (Leonids week) | 4 | 5 | 4 | 5 | 5 | 4 | 2 | 5 | 3 | 83.9 | WS-018 | Selected, conditional on verification
T088 | The last bus out before the pass closes (cast assembles; bridge to December) | P1 | [J] | W | 4 | 5 | 4 | 4 | 4 | 4 | 1 | 5 | 2 | 76.6 | WS-030 | Selected (bridge)
T089 | Lightning on a hike: the picnic shelter won't save you | P2 | [BK]; [LEDGER C-R101–104] | Summer/E | 4 | 5 | 3 | 4 | 3 | 4 | 4 | 5 | 4 | 80.5 | R01 | Reserve (verified)
T090 | Cold water overboard: the gasp comes first | P2 | [LEDGER C-2101/2102] | E | 4 | 4 | 3 | 4 | 3 | 3 | 4 | 5 | 3 | 73.2 | R08 | Reserve (verified)
T091 | Airport gate on the busiest travel day | P1 | [J] + calendar (day before Thanksgiving) | T | 4 | 5 | 4 | 4 | 4 | 4 | 2 | 5 | 3 | 80.0 | WS-026 | Selected
T092 | Infected can't climb ladders: the grain silo | P1 | [J] | E | 3 | 4 | 3 | 4 | 3 | 3 | 1 | 3 | 3 | 62.0 | REJ | Rural silo reads as reference territory
T093 | Black ice on the bridge: the skid decision | P2 | [BK] | W | 4 | 4 | 3 | 4 | 3 | 3 | 1 | 4 | 4 | 68.8 | DEF | Unverified driving guidance
T094 | Outbreak during a power outage at the hospital nursery | P1 | [J] | E | 3 | 4 | 3 | 3 | 3 | 3 | 1 | 2 | 3 | 58.0 | REJ | Infants in peril: brand-safety

## Claims
Claim ID | Claim | Class | Source (org, URL/ref) | Assumptions | Necessary qualification | Script wording | Visual implication | Verification status | Episodes | Verified by | Verified on | Exact quote (paste) | URL
C-011 | Private wells with electric (submersible) pumps stop delivering water when the power fails | FACT | PA Dept. of Health private well factsheet; Michigan EGLE (see research appendix D2 §1a) | Electric pump, no backup power | Hand pumps / gravity systems differ | "His well runs on an electric pump. No power, no water." | Diagram: power → pump → tap | SUPPORTED | REF02; WS-010
C-012 | Portable generator noise: Honda EU2200i inverter 57 dB(A) (full load) and EB10000 open-frame 73 dB(A), both at 7 m / 23 ft | FACT | Honda Power Equipment model pages and generator brochure (powerequipment.honda.com) | Manufacturer test conditions | Varies by model and load | Use ranges, not single numbers | Amber Sphere radius must be plausible | SUPPORTED | REF01/02; WS-003; WS-005
C-013 | Outdoors, sound from a point source falls about 6 dB per doubling of distance (free field) | FACT | OSHA noise pages (osha.gov/noise; OSHA Technical Manual III-5); FHWA construction noise handbook | Ideal free field | Wind, terrain, air absorption and background noise change real audibility | "Sound fades with distance, but in a silent town it carries." | Sphere fades in opacity with distance | SUPPORTED | WS-003; WS-013
C-020 | Reference story claim: 73 gallons lets a farm with 12 cattle, 1 horse, 30 hens, a dog and a farmer 'survive for weeks' | FACT (audit) | Oklahoma State Ext. (beef cows 8.2–13.4 gal/day @40–90°F); NDSU; Purdue/UMN/Iowa State (horse ~10–18 gal/day); Penn State/K-State/UKY (hens 5–10.6 gal/100 birds/day); Cornell/TAMU (dog) | Non-lactating 1,100 lb cows | — | — | — | FALSE (≈110–183 gal/day needed; 73 gal lasts <1 day) | REF02
C-021 | Reference story claim: a generator heard across ~3 miles (4.8 km) of fields | FACT (audit) | Derived: C-012 + C-013 (57–73 dB(A)@7 m minus 20·log10(4800/7) ≈ 56.7 dB → ≈0–16 dB(A) before air absorption) | Spherical spreading only | Quiet nights, wind and terrain can extend audibility; air absorption reduces it | — | — | QUALIFIED (doubtful at that distance) | REF01
C-022 | Bathtub water stored before a storm is for flushing and cleaning, not drinking unless the tub is clean and the water treated | FACT | NWS hurricane safety PDF; UF/IFAS FS131; CDC flood guidance | — | Follow local advice | "Tub water is for flushing, not drinking." | Label tub 'FLUSHING' | QUALIFIED | WS-010
C-101 | Exhaled breath becomes visible as condensation in cold air | FACT | General atmospheric physics (condensation of warm moist breath in cold air). No agency page retrieved this session | Cold, fairly humid night | Visibility depends on temperature and humidity; no fixed threshold stated | "On a cold night, you can see living people breathe." (no number) | Breath puffs only outdoors in cold; indoors warm = no puffs | UNVERIFIED (low risk; add one citable source, e.g. a NOAA/NWS or university explainer) | WS-001
C-102 | The Turned do not breathe (no breath fog) | FICTION | WR-02 | — | Fiction scenario label | "The Turned don't breathe." | No puffs on Turned; plant several in background shots | FICTION | WS-001; WS-009; WS-016
C-103 | The Turned can push but cannot pull doors or turn handles | FICTION | WR-04 | — | — | — | Door arrows | FICTION | WS-001; WS-003; WS-011; WS-013; WS-019
C-104 | In-story emergency alert must not copy the real Wireless Emergency Alert layout | DESIGN RULE | YouTube violent/graphic policy context on fictional footage needing clear context (research appendix B §8) | — | — | Use an original 'CITY ALERT' card design | Stylised, clearly animated UI | DESIGN RULE | WS-001
C-201 | In field tests, vehicles floated about 15–63 s before water reached the bottom of the side windows | FACT | Giesbrecht & McDonald 2010, Aviat Space Environ Med (PubMed 20681239) | Calm water, small sample | Times vary by vehicle and conditions | "In tests, cars floated about 15 seconds to a minute before water reached the windows." | T1 timer starts ≈00:60 and is labelled 'about' | SUPPORTED (confirm abstract wording) | WS-002
C-202 | Water pressure pins the doors; they usually won't open until the car is almost full | FACT | Giesbrecht & McDonald 2010 (PubMed 20681239); University of Manitoba (Giesbrecht faculty page) | — | — | "Water is pressing on the door. It won't open until the car is nearly full." | Cyan pressure arrows on door; Owen's push fails | SUPPORTED | WS-002
C-203 | Escape is easiest during the initial floating phase, through a side window | FACT | Giesbrecht & McDonald 2010; U. Manitoba | — | — | "The way out is the window, while the car is still floating." | Window exit before waterline reaches glass | SUPPORTED | WS-002
C-204 | You have about one minute to exit safely (a car may float up to ~3 minutes) | FACT | University of Manitoba (Giesbrecht) — paraphrase via search extract | — | Rule of thumb | "You have about one minute." | — | QUALIFIED (confirm live wording) | WS-002
C-205 | Order of the first two actions: seatbelt off then window, or window then seatbelt | FACT | U. Manitoba lists 'Seatbelts off, Windows open… Out'; CBS (2024) reports Giesbrecht reversed the order — not confirmed | — | — | Script carries Version A and Version B; use the order in the current Giesbrecht/U. Manitoba guidance | Animatic must match the chosen order | UNVERIFIED — BLOCKING | WS-002
C-206 | Keep a window-breaking tool within the driver's reach; break a side window, not the windshield | FACT | McDonald & Giesbrecht 2013 review (Aviat Space Environ Med; PDF via Kids and Cars); Giesbrecht via CBS | — | Some newer vehicles have laminated side glass that tools may not break (UNVERIFIED) — mention in description only | "Keep a window tool where you can reach it." | Punch tool on Owen's keyring hits corner of side window | QUALIFIED | WS-002
C-207 | Laminated side glass may resist window-punch tools | FACT | NHTSA / manufacturers (not verified) | — | — | Not on screen | — | UNVERIFIED (description caveat only) | WS-002
C-401 | Drop, Cover, and Hold On is the recommended action during shaking | FACT | Earthquake Country Alliance handout (State of Alaska DHS&EM); USGS 'What should I do during an earthquake?' | — | If no table: cover head/neck against an interior wall | "Drop. Cover. Hold on." | Drop to knees, under sturdy table, hold the leg | SUPPORTED | WS-004
C-402 | In modern homes doorways are no stronger than other parts of the house, and the door can swing and injure you | FACT | USGS 'Earthquake facts & fantasy'; FEMA P-530 | Modern construction | Old adobe houses are the myth's origin | "A doorway is no stronger than any other wall, and the door can swing into you." | Door swings shut on the doorway-stander | SUPPORTED | WS-004
C-403 | Don't run outside during shaking; leave a damaged building after shaking stops | FACT | USGS FAQ; USGS HVO; Ready.gov | — | Outdoors already: stay in the open away from buildings and lines | "Don't run while it's shaking. When it stops, if the building is damaged, get out." | Glass falls near exit during shaking | QUALIFIED | WS-004
C-404 | Aftershocks can follow for hours to months | FACT | FEMA fact sheet; USGS; Ready.gov | — | Usually smaller | "Then the aftershock." | Second smaller shake; repeat pose | SUPPORTED | WS-004
C-501 | Never run a portable generator indoors or in a garage, even with doors or windows open | FACT | CPSC 2026 news releases on generator CO | — | — | "Never in the garage. Not even with the door open." | Garage door half open, Gas-Violet Sphere filling the house | SUPPORTED | WS-005; WS-010
C-502 | Keep a generator at least 20 ft (6 m) from windows, doors and vents | FACT | CDC CO PSA toolkit; FEMA | — | Agencies vary slightly in wording; 20 ft is the CDC figure | "At least twenty feet from the house." | Measured tick on Sphere: '≥20 FT' | SUPPORTED | WS-005
C-503 | Carbon monoxide is colourless and odourless | FACT | CDC clinical guidance; CDC blog | — | — | "You can't see it. You can't smell it." | Violet Sphere is the only visual cue | SUPPORTED | WS-005
C-504 | CO poisoning symptoms include headache, dizziness, weakness, nausea and confusion | FACT | CDC HAN 2020 (archive.cdc.gov) | — | Symptoms can resemble flu; sleeping people may not wake | "Headache. Dizzy. Sleepy. That's not the flu." | Neighbour rubbing temples | SUPPORTED | WS-005
C-505 | Install battery-backed CO alarms | FACT | CDC/CPSC (commonly advised; not retrieved this session) | — | — | REAL RULE line option | Alarm on wall chirping | UNVERIFIED — BLOCKING if used | WS-005
C-506 | If carbon monoxide poisoning is suspected, get everyone out into fresh air right away and call emergency services | FACT | CDC / CPSC first-response guidance (07 §4 standard wording; the specific page wording was not retrieved this session) | — | No medical advice beyond this first response | "Fresh air first. Then call for help." | Owen walks the family out into the snow before anything else; phone call outside | UNVERIFIED — BLOCKING | WS-005
C-801 | Do not shelter under a highway overpass; wind can accelerate (tunnelling) | FACT | NWS Birmingham safety rules; NWS Mobile; NOAA report on 3 May 1999 outbreak | — | — | "An overpass can funnel the wind and the debris right at you." | Never show overpass as safe | SUPPORTED | WS-008
C-802 | If caught in a vehicle: drive out of the storm's path if possible (at right angles to its track); otherwise get down in a ditch or culvert lower than the road and cover your head | FACT | NWS Mobile / Milwaukee offices (paraphrase via extract) | — | Depends on traffic and debris; confirm live wording | "If you can't drive away, get lower than the road and cover your head." | Tess lies in a ditch, arms over head | QUALIFIED (confirm live wording) | WS-008
C-803 | A tornado watch means be prepared; a warning means take action now | FACT | NWS Weather-Ready Nation | — | — | "A watch means get ready. A warning means go." | Phone shows WARNING in red | SUPPORTED | WS-008
C-804 | Many survivors describe a roar like a freight train | FACT | Ready.gov; NOAA SPC FAQ; NSSL | — | Sound varies; downbursts sound similar; don't wait to hear it | "Some people hear a roar like a train. Don't wait for it." | Rising rumble | QUALIFIED | WS-008
C-1001 | Refrigerator keeps food safe about 4 hours without power; a full freezer about 48 hours, half-full about 24 (doors closed) | FACT | FoodSafety.gov power-outage chart; USDA FSIS | Doors kept closed | — | "Fridge: about four hours. Full freezer: about two days." | T1 timers on fridge/freezer | SUPPORTED | WS-010; WS-014
C-1002 | Store at least 1 gallon of water per person per day | FACT | Ready.gov water; CDC emergency water supply | — | More for heat, children, pets | "One gallon per person, per day." | Counter | SUPPORTED | WS-010; WS-014
C-1003 | Cell sites and gas station pumps depend on electricity / backup power | FACT | (not retrieved) | — | Backup durations vary widely | Avoid specific hours | — | UNVERIFIED — BLOCKING if stated | WS-010
C-1101 | Building-specific door directions (stairwell / emergency exit doors open in the direction of exit travel) | FACT | Building codes (IBC / NFPA 101) — not retrieved | — | Varies by building | Keep as story fact for *this* building: "In Tess's building, the stairwell doors push inward." | Arrows | UNVERIFIED (treat as in-story fact only) | WS-011; WS-013
C-1201 | A home fire can become life-threatening in as little as about two minutes | FACT | Ready.gov home fires; American Red Cross; UL (escape time ≤3 min) | — | — | "You may have about two minutes." | T1 timer 02:00 | SUPPORTED | WS-012
C-1202 | A closed door holds back heat and smoke ('Close Before You Doze'): in UL FSRI tests closed-door rooms stayed under ~100 °F vs over 1,000 °F with the door open | FACT | UL FSRI Close Before You Doze (fsri.org) and full-scale test notes | Test conditions | Avoid CO figures (sources disagree) | "A closed door can keep a room hundreds of degrees cooler." | Split: open vs closed bedroom | SUPPORTED | WS-012
C-1203 | Get low and crawl under smoke | FACT | NFPA escape planning; USFA pictographs | — | — | "Get low. Go." | Crawl | SUPPORTED | WS-012
C-1204 | Once out, stay out; never go back inside | FACT | Ready.gov home fire escape plan | — | — | "Get out. Stay out." | Owen stops at the door | SUPPORTED | WS-012
C-1205 | Feel a closed door with the back of your hand before opening | FACT | NFPA / Red Cross (common guidance; not retrieved) | — | — | "Back of the hand. Hot? Use the window." | Hand to door | UNVERIFIED — BLOCKING if used | WS-012
C-1206 | Plan two ways out of every room; a window can be the second way out when smoke blocks the door route | FACT | NFPA home fire escape planning; USFA escape-planning pictographs (pages cited in research appendix D2 §3c; this wording not retrieved) | Ground floor or a safe low roof; never jump from height | Only where the window leads somewhere safe | "Every room needs a second way out." | Window opens onto the porch roof; Owen moves slowly and low | UNVERIFIED — BLOCKING | WS-012
C-1501 | Antarctic winter temperatures at inland stations fall far below −30 °C | FACT | (not retrieved; e.g. British Antarctic Survey / NSF) | — | Coastal stations are milder | Keep as story setting with a stated temperature | Thermometer HUD | UNVERIFIED — BLOCKING if a number is shown | WS-015; WS-016
C-1701 | If caught in a rip current: relax and float, don't swim against it; swim parallel to shore; if you can't escape, face shore and wave for help | FACT | NWS Mount Holly CFW product; NWS rip current safety; NOAA NOS | — | — | "Don't fight it. Float. Then swim sideways." | Overhead shot: sideways exit | SUPPORTED | WS-017
C-1702 | Most rip currents are less than about 80 ft wide | FACT | NOAA National Ocean Service tutorial (paraphrase) | — | 'Most', not all | "Most are narrower than a basketball court is long." (or "less than about 25 metres") | Width tick on Cyan Sphere | QUALIFIED | WS-017
C-1703 | US rip-current deaths: about 100 a year (estimate); NWS counted 74 in 2024 | FACT | NOAA Ocean Today; NWS ILM/USLA; NWS 2024 hazard summary | — | Estimates vary | Prefer no number on screen | — | QUALIFIED | WS-017
C-1704 | Visual signs of a rip (gap in breaking waves, churning/discoloured water) | FACT | NOAA (not retrieved) | — | — | — | Only animate after verification | UNVERIFIED — BLOCKING if shown | WS-017
C-1801 | Chelyabinsk, 15 Feb 2013: a meteor airburst's shock wave arrived after the flash and blew out windows; most of ~1,500 injuries were from broken glass | FACT | NASA / ESA (not retrieved) | — | — | "In 2013, most people hurt in Chelyabinsk were hit by window glass." | Flash → delay → glass | UNVERIFIED — BLOCKING | WS-018
C-1802 | Leonid meteor shower 2026 peak date; meteor-shower meteors are tiny particles that burn up and are harmless | FACT | IMO / American Meteor Society / NASA (not retrieved) | — | Must not imply the Leonids cause airbursts | "Tonight's meteors are dust. Harmless." | — | UNVERIFIED — BLOCKING | WS-018
C-1901 | Elevator free fall is extremely rare (multiple ropes and safety brakes) but not impossible | FACT | Otis high-rise safety; WTAMU physics Q&A; Ole Miss eGrove (research appendix D2 §4a) | — | Rare ≠ impossible | "Elevators almost never fall." | — | QUALIFIED | WS-019
C-1902 | If stuck in an elevator: stay inside, use the alarm/phone, don't force the doors | FACT | Otis '5 steps to take if your elevator stops'; Technical Safety BC | — | — | "Stay in. Press the alarm. Don't pry the doors." | Alarm button glow | SUPPORTED | WS-019
C-2001 | Carrington Event (1859); Quebec blackout (13 Mar 1989, ~9 hours); May 2024 G5 storm; severe storms can damage high-voltage transformers | FACT | NOAA SWPC; NASA; Hydro-Québec (not retrieved) | — | Impacts uncertain; avoid apocalyptic certainty | — | Aurora at low latitude; transformer hum | UNVERIFIED — BLOCKING | WS-020
C-2101 | Cold-water shock: an involuntary gasp and rapid breathing in the first minute (can last up to ~3 minutes) | FACT | NIH/PMC peer-reviewed reviews; NWS cold water safety | — | — | "First comes the gasp. Control your breathing." | Tess gasps, then slows breathing | SUPPORTED | WS-021
C-2102 | '1-10-1': about 1 minute to control breathing, ~10 minutes of meaningful movement, up to ~1 hour before unconsciousness | FACT | NPS Point Reyes; Giesbrecht (McGill OSS) | — | Rough guide; varies widely | "About a minute to breathe. About ten to get out." | T1 timer 1:00 → 10:00 | QUALIFIED | WS-021
C-2103 | Self-rescue: turn back toward where you came (strongest ice), get arms on the ice, kick, slide out, roll away; don't stand until on solid ice | FACT | Minnesota DNR; Wisconsin DNR; Michigan DNR | — | — | "Turn back the way you came. Kick. Slide. Roll." | Exact sequence | SUPPORTED | WS-021
C-2104 | Minimum ice thickness guidance for walking (e.g. 4 in. of new clear ice) | FACT | MN DNR ice thickness guidelines (not retrieved) | — | — | — | — | UNVERIFIED — BLOCKING if a number is shown | WS-021
C-2301 | 'Ready, Set, Go!' — leave early when told; embers can ignite homes far ahead of the flame front | FACT | CAL FIRE / IAFC Ready Set Go; NFPA Firewise (not retrieved) | — | — | — | — | UNVERIFIED — BLOCKING | WS-023
C-2501 | Avalanche burial survival falls sharply after about 15–18 minutes; companion rescue with beacon, probe and shovel | FACT | Brugger/Haegeli survival-curve research; avalanche.org (not retrieved) | — | — | — | — | UNVERIFIED — BLOCKING | WS-025
C-2701 | Thanksgiving is the peak day for US home cooking fires; never use water on a grease fire (cover, turn off heat); turkey fryers outdoors away from buildings, turkey fully thawed | FACT | NFPA; USFA; UL (not retrieved) | — | — | — | — | UNVERIFIED — BLOCKING | WS-027
C-2801 | Crowd crush risk rises sharply at high densities (≈5+ people per m²); guidance for individuals (stay upright, protect chest, move diagonally with gaps) | FACT | G. Keith Still crowd science; agency guidance (not retrieved) | — | Sensitive topic | — | No depiction of deaths | UNVERIFIED — BLOCKING | WS-028
C-2901 | Stranded in a winter storm: stay with the vehicle; keep the exhaust pipe clear of snow (CO); run the engine about 10 minutes per hour for heat; make the car visible | FACT | NWS winter safety; Ready.gov winter weather (not retrieved) | — | — | — | — | UNVERIFIED — BLOCKING | WS-029
C-1401 | A 2015 Cornell zombie-outbreak model found dense cities fall fastest and sparsely populated regions last longest | FACT (about a model) | Coverage of Alemi et al. (Cornell) model via news (research appendix C, R-S36) | It's a model of a fictional outbreak | — | "Even scientists who modelled a zombie outbreak said: get away from dense cities." | Map of spread | QUALIFIED (confirm the original paper) | WS-014
C-R101 | There is no safe place outdoors in a thunderstorm; if you can hear thunder you are likely within striking distance | FACT | NWS lightning safety overview (weather.gov/safety/lightning) | — | — | "If you can hear thunder, you're close enough to be struck." | Picnic shelter is NOT safe | SUPPORTED | R01
C-R102 | Safe shelter: a substantial building or a hard-topped metal vehicle with windows up; stay 30 minutes after the last thunder | FACT | NOAA JetStream lightning safety; NWS | — | — | "Get inside. Wait thirty minutes after the last thunder." | T1 timer resets on each rumble | SUPPORTED | R01
C-R103 | The lightning crouch does not provide meaningful protection; NWS stopped recommending it in 2008 | FACT | NWS lightning-crouch page; NOAA JetStream FAQ | — | Never show crouch as the hero's solution | "Crouching won't save you." | — | SUPPORTED | R01
C-R104 | Rubber tyres don't protect you; a hard-topped car's metal shell does | FACT | NWS lightning myths; NWS Melbourne | — | Hands off metal | "It's the metal roof, not the rubber tyres." | Current flows around the car body | SUPPORTED | R01
C-R201 | Never drive or walk into floodwater ('Turn Around Don't Drown') | FACT | NWS Turn Around Don't Drown | — | — | "Turn around. Don't drown." | Car reverses at the flooded dip | SUPPORTED | R02
C-R202 | Six inches of fast-moving water can knock over an adult | FACT | NWS Turn Around Don't Drown | — | — | "Six inches of fast water can knock you down." | Shin-deep current | SUPPORTED | R02
C-R203 | About 12 inches of rushing water can carry away most cars; 2 feet can carry away SUVs and trucks | FACT | NWS Turn Around Don't Drown; NWS Tulsa | — | 'Most cars' (not 'a small car') | "About a foot of rushing water can float most cars." | Water at bumper height lifts car | QUALIFIED | R02
C-R204 | More than half of flood drownings involve vehicles driven into flood water | FACT | NWS (citing CDC); NWS WRN social kit | — | — | "Most flood deaths happen in cars." | — | SUPPORTED | R02
C-P01 | Animated or clearly unrealistic content does not require YouTube's altered/synthetic disclosure | PLATFORM | YouTube Blog (Mar 2024) 'Disclosing AI-generated content' | — | Realistic synthetic people/events would | — | — | SUPPORTED | All
C-P02 | Videos uploaded since 15 Oct 2024 that are square/vertical and ≤3 minutes are Shorts | PLATFORM | YouTube Help answer 15424877 | — | — | — | — | SUPPORTED | All

## Schedule
Day | Publish | ID | Cx | Research start | Claims verified | Script lock | Animatic + VO | Assets ready | Animation done | QA + export (banked) | Actual banked date | Bank level that day | Notes
1 | 2026-10-31 | WS-001 | H | pre-launch | 2026-10-17 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | 2026-10-28
2 | 2026-11-01 | WS-002 | M | pre-launch | 2026-10-17 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | 2026-10-28
3 | 2026-11-02 | WS-003 | H | pre-launch | 2026-10-17 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | 2026-10-28
4 | 2026-11-03 | WS-004 | L | pre-launch | 2026-10-17 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | 2026-10-28
5 | 2026-11-04 | WS-005 | M | pre-launch | 2026-10-17 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | 2026-10-28
6 | 2026-11-05 | WS-006 | H | pre-launch | 2026-10-21 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | 2026-11-02
7 | 2026-11-06 | WS-007 | M | pre-launch | 2026-10-21 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | see 20 §2.3 | 2026-11-03
8 | 2026-11-07 | WS-008 | M | 2026-10-24 | 2026-10-28 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-03 | 2026-11-04
9 | 2026-11-08 | WS-009 | M | 2026-10-25 | 2026-10-29 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-04 | 2026-11-05
10 | 2026-11-09 | WS-010 | M | 2026-10-26 | 2026-10-30 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-05 | 2026-11-06
11 | 2026-11-10 | WS-011 | M | 2026-10-27 | 2026-10-31 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-06 | 2026-11-07
12 | 2026-11-11 | WS-012 | M | 2026-10-28 | 2026-11-01 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-07 | 2026-11-08
13 | 2026-11-12 | WS-013 | M | 2026-10-29 | 2026-11-02 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-08 | 2026-11-09
14 | 2026-11-13 | WS-014 | M | 2026-10-30 | 2026-11-03 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-09 | 2026-11-10
15 | 2026-11-14 | WS-015 | H | 2026-10-31 | 2026-11-04 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-10 | 2026-11-11
16 | 2026-11-15 | WS-016 | M | 2026-11-01 | 2026-11-05 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-11 | 2026-11-12
17 | 2026-11-16 | WS-017 | M | 2026-11-02 | 2026-11-06 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-13
18 | 2026-11-17 | WS-018 | M | 2026-11-03 | 2026-11-07 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-13 | 2026-11-14
19 | 2026-11-18 | WS-019 | L | 2026-11-04 | 2026-11-08 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-14 | 2026-11-15
20 | 2026-11-19 | WS-020 | M | 2026-11-05 | 2026-11-09 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-15 | 2026-11-16
21 | 2026-11-20 | WS-021 | M | 2026-11-06 | 2026-11-10 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-16 | 2026-11-17
22 | 2026-11-21 | WS-022 | H | 2026-11-07 | 2026-11-11 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-17 | 2026-11-18
23 | 2026-11-22 | WS-023 | M | 2026-11-08 | 2026-11-12 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-18 | 2026-11-19
24 | 2026-11-23 | WS-024 | L | 2026-11-09 | 2026-11-13 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-19 | 2026-11-20
25 | 2026-11-24 | WS-025 | M | 2026-11-10 | 2026-11-14 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-20 | 2026-11-21
26 | 2026-11-25 | WS-026 | M/H | 2026-11-11 | 2026-11-15 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-21 | 2026-11-22
27 | 2026-11-26 | WS-027 | L | 2026-11-12 | 2026-11-16 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-22 | 2026-11-23
28 | 2026-11-27 | WS-028 | M | 2026-11-13 | 2026-11-17 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-23 | 2026-11-24
29 | 2026-11-28 | WS-029 | M | 2026-11-14 | 2026-11-18 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-24 | 2026-11-25
30 | 2026-11-29 | WS-030 | H | 2026-11-15 | 2026-11-19 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-25 | 2026-11-26

## Pilot hours
Episode | Tier | Stage (12 §5) | Estimate (h) | Actual (h) | Notes
WS-001 | H | Topic + research + claims | 1.5
WS-001 | H | Rules + hook + script + timed read | 2.5
WS-001 | H | Storyboard / animatic | 1.5
WS-001 | H | Assets | 4
WS-001 | H | Animation | 8
WS-001 | H | Voice | 1
WS-001 | H | Edit + captions | 1.5
WS-001 | H | Sound + mix | 1.5
WS-001 | H | QA + export + package | 1
WS-002 | M | Topic + research + claims | 1
WS-002 | M | Rules + hook + script + timed read | 2
WS-002 | M | Storyboard / animatic | 1
WS-002 | M | Assets | 1.5
WS-002 | M | Animation | 5
WS-002 | M | Voice | 0.75
WS-002 | M | Edit + captions | 1.25
WS-002 | M | Sound + mix | 1
WS-002 | M | QA + export + package | 0.75
WS-003 | H | Topic + research + claims | 1.5
WS-003 | H | Rules + hook + script + timed read | 2.5
WS-003 | H | Storyboard / animatic | 1.5
WS-003 | H | Assets | 4
WS-003 | H | Animation | 8
WS-003 | H | Voice | 1
WS-003 | H | Edit + captions | 1.5
WS-003 | H | Sound + mix | 1.5
WS-003 | H | QA + export + package | 1
Total estimate / actual
Actual ÷ estimate (if >1.15, see 20 §5)

## Tracking
ID | Publish date | Checkpoint | Public views | Engaged views | Stayed to watch % | AVD (s) | APV % | Ret. 3 s % | Ret. 50% % | Ret. at Fork % | Shares | Subscribers gained | Comments | Valid corrections | Confusion comments | Share rate /1k engaged | Subscribe rate /1k engaged | Comment rate /1k engaged | Correction rate /100 comments | Confusion rate /100 comments | Notes
WS-001 | 2026-10-31 | 24 h
WS-001 | 2026-10-31 | 72 h
WS-001 | 2026-10-31 | 7 d
WS-002 | 2026-11-01 | 24 h
WS-002 | 2026-11-01 | 72 h
WS-002 | 2026-11-01 | 7 d
WS-003 | 2026-11-02 | 24 h
WS-003 | 2026-11-02 | 72 h
WS-003 | 2026-11-02 | 7 d
WS-004 | 2026-11-03 | 24 h
WS-004 | 2026-11-03 | 72 h
WS-004 | 2026-11-03 | 7 d
WS-005 | 2026-11-04 | 24 h
WS-005 | 2026-11-04 | 72 h
WS-005 | 2026-11-04 | 7 d
WS-006 | 2026-11-05 | 24 h
WS-006 | 2026-11-05 | 72 h
WS-006 | 2026-11-05 | 7 d
WS-007 | 2026-11-06 | 24 h
WS-007 | 2026-11-06 | 72 h
WS-007 | 2026-11-06 | 7 d
WS-008 | 2026-11-07 | 24 h
WS-008 | 2026-11-07 | 72 h
WS-008 | 2026-11-07 | 7 d
WS-009 | 2026-11-08 | 24 h
WS-009 | 2026-11-08 | 72 h
WS-009 | 2026-11-08 | 7 d
WS-010 | 2026-11-09 | 24 h
WS-010 | 2026-11-09 | 72 h
WS-010 | 2026-11-09 | 7 d
WS-011 | 2026-11-10 | 24 h
WS-011 | 2026-11-10 | 72 h
WS-011 | 2026-11-10 | 7 d
WS-012 | 2026-11-11 | 24 h
WS-012 | 2026-11-11 | 72 h
WS-012 | 2026-11-11 | 7 d
WS-013 | 2026-11-12 | 24 h
WS-013 | 2026-11-12 | 72 h
WS-013 | 2026-11-12 | 7 d
WS-014 | 2026-11-13 | 24 h
WS-014 | 2026-11-13 | 72 h
WS-014 | 2026-11-13 | 7 d
WS-015 | 2026-11-14 | 24 h
WS-015 | 2026-11-14 | 72 h
WS-015 | 2026-11-14 | 7 d
WS-016 | 2026-11-15 | 24 h
WS-016 | 2026-11-15 | 72 h
WS-016 | 2026-11-15 | 7 d
WS-017 | 2026-11-16 | 24 h
WS-017 | 2026-11-16 | 72 h
WS-017 | 2026-11-16 | 7 d
WS-018 | 2026-11-17 | 24 h
WS-018 | 2026-11-17 | 72 h
WS-018 | 2026-11-17 | 7 d
WS-019 | 2026-11-18 | 24 h
WS-019 | 2026-11-18 | 72 h
WS-019 | 2026-11-18 | 7 d
WS-020 | 2026-11-19 | 24 h
WS-020 | 2026-11-19 | 72 h
WS-020 | 2026-11-19 | 7 d
WS-021 | 2026-11-20 | 24 h
WS-021 | 2026-11-20 | 72 h
WS-021 | 2026-11-20 | 7 d
WS-022 | 2026-11-21 | 24 h
WS-022 | 2026-11-21 | 72 h
WS-022 | 2026-11-21 | 7 d
WS-023 | 2026-11-22 | 24 h
WS-023 | 2026-11-22 | 72 h
WS-023 | 2026-11-22 | 7 d
WS-024 | 2026-11-23 | 24 h
WS-024 | 2026-11-23 | 72 h
WS-024 | 2026-11-23 | 7 d
WS-025 | 2026-11-24 | 24 h
WS-025 | 2026-11-24 | 72 h
WS-025 | 2026-11-24 | 7 d
WS-026 | 2026-11-25 | 24 h
WS-026 | 2026-11-25 | 72 h
WS-026 | 2026-11-25 | 7 d
WS-027 | 2026-11-26 | 24 h
WS-027 | 2026-11-26 | 72 h
WS-027 | 2026-11-26 | 7 d
WS-028 | 2026-11-27 | 24 h
WS-028 | 2026-11-27 | 72 h
WS-028 | 2026-11-27 | 7 d
WS-029 | 2026-11-28 | 24 h
WS-029 | 2026-11-28 | 72 h
WS-029 | 2026-11-28 | 7 d
WS-030 | 2026-11-29 | 24 h
WS-030 | 2026-11-29 | 72 h
WS-030 | 2026-11-29 | 7 d

## QA log
ID | Export file + version | Reviewer | Device | Date | S | F | V | W | A | P (playback on export) | U / notes
WS-001
WS-002
WS-003
WS-004
WS-005
WS-006
WS-007
WS-008
WS-009
WS-010
WS-011
WS-012
WS-013
WS-014
WS-015
WS-016
WS-017
WS-018
WS-019
WS-020
WS-021
WS-022
WS-023
WS-024
WS-025
WS-026
WS-027
WS-028
WS-029
WS-030

## Change log
ID | Date | Change | Why (evidence) | Files
CL-001 | 2026-10-14 | All Fork-time captions moved to lane A (tag drawn above the crack) | Lane B overlapped the Fork chips (found while prototyping) | 09 §6, packages
CL-002 | 2026-10-14 | 13 Verdict factors shortened to ≤8 words | The V2 rule (≤8 words) was broken in the first calendar draft | calendar_data, briefs
CL-003 | 2026-10-14 | Day 1 script trimmed to 121 words; read rate set to 2.85 words/s | The first draft implied ≈250 wpm windows | WS-001 package
CL-004 | 2026-10-14 | WS-002 countdown made real time (T1 per-second events) | The first draft showed a time inconsistent with screen time (a false countdown) | WS-002 package
CL-005 | 2026-10-14 | WS-005 REAL RULE shortened from 16 to 14 words | The V3 limit is ≤14 words | calendar, WS-005 brief
CL-006 | 2026-10-14 | WS-026 title no longer says "Busiest Travel Day" | No ledger source; replaced by a plain calendar fact ("the Day Before Thanksgiving") | calendar, WS-026 brief
CL-007 | 2026-10-14 | SAFE added as a Verdict status; WS-010 "OK" changed to SAFE | Real Rule outcomes needed a truthful status that isn't "escaped" | 08 §8.3, 09 V1, calendar
CL-008 | 2026-10-14 | WR-04 extended: no climbing over waist-high barriers | WS-006's cart barrier needed the rule stated before use (rules never change to rescue a character) | 07 §3, WS-006 brief
CL-009 | 2026-10-14 | Ledger rows C-506 (CO first response) and C-1206 (second way out) added as BLOCKING | Scripts used these instructions without ledger rows | ledger, WS-005, WS-012
CL-010 | 2026-10-14 | Fallback launch order re-flowed so seasonal episodes keep their dates | "Same order, 9 days later" would have mis-dated the Thanksgiving and Black Friday episodes | 17, 20 §2.4
CL-011 | 2026-10-14 | WS-003 target duration revised from 62–66 s to 58–62 s; Verdict statuses normalised to the fixed set (CONTAINED/READY/OUT/FOUND mapped to SURVIVED/SAFE/ESCAPED) | The timed package reads 58.0 s; one status vocabulary keeps the Verdict ritual consistent | calendar, WS-003/015/020/021/023/025 briefs
CL-012

## Asset register
Asset ID | Asset | Type | Creator / source | Licence | Proof location | Allowed in monetized YouTube? | Attribution required | Used in | Date logged | Notes
AR-001 | Big Shoulders Display (800/900) | Font | @fontsource/big-shoulders-display 5.3.0 (Google Fonts family) | SIL OFL 1.1 | tools/render/fonts/LICENSE_big-shoulders-display.txt | Yes (burned-in output is not covered by the OFL) | No | Typography system (09); all episodes | 2026-10-14 | Licence text read from the package file
AR-002 | Atkinson Hyperlegible Next (400/700/800) | Font | @fontsource/atkinson-hyperlegible-next 5.3.0 (Braille Institute; Google Fonts) | SIL OFL 1.1 | tools/render/fonts/LICENSE_atkinson-hyperlegible-next.txt | Yes | No | Captions and Verdict text; all episodes | 2026-10-14 | Licence text read from the package file
AR-003 | JetBrains Mono (700/800) | Font | @fontsource/jetbrains-mono 5.3.0 (JetBrains) | SIL OFL 1.1 | tools/render/fonts/LICENSE_jetbrains-mono.txt | Yes | No | Timers, labels, tags; all episodes | 2026-10-14 | Licence text read from the package file
AR-004 | Style frames SF1–SF3 and motion proof MP1 | Image/video (prototype) | Original; rendered in this project from procedural code (tools/render) | Owned by the channel owner (original work) | 11_Style_Frames_and_Motion_Proof/ | Yes | No | Reference only (not for publication as-is) | 2026-10-14 | Silent; no third-party media
AR-005 | Type and Verdict specimens; safe-zone overlay | Image | Original (tools/render) | Owned (original work) | 09_Typography_and_Captions/ | Yes | No | Production reference | 2026-10-14 | The overlay is a planning aid based on Google's Shorts ads guidance
AR-006 | Caption style sheet (worldosphere_caption_styles.ass) | Text | Original | Owned (original work) | 09_Typography_and_Captions/ | Yes | No | All episodes | 2026-10-14 | —
AR-007 | Worldosphere motif (two-note) | Audio | TO BE CREATED (original composition) | Owned once composed | 00_Library/Audio/MOTIF/ (production) | Yes once original | No | All episodes | — | Not yet produced
AR-008 | Pulse beds 70/76/90 BPM | Audio | TO BE CREATED (original) or a licensed library track | Depends on source | — | Only with a monetization-cleared licence | Depends | All episodes | — | Avoid claimable music in Shorts over 60 s until the Content ID rule is verified (23 §2)
AR-009 | Core SFX set (Fork whoosh/tick; Verdict slide/boom; Sphere bloom) | Audio | TO BE CREATED (original Foley) or Sonniss GDC bundle | Owned / Sonniss licence | — | Yes (Sonniss terms as seen; verify the 2026 PDF) | No | All episodes | — | Keep the Sonniss licence PDF with the files
AR-010 | Narrator voice | Audio | TO BE DECIDED (own voice / contracted actor / licensed synthetic) | Depends | — | Only with written commercial terms | Depends | All episodes | — | See 22 §4